## Summary
Hireup JIRA Scope Analysis
Date: 16 April 2026 (Revised after multi-agent review)
Prepared by: 2cloudnine
SOW: No. 20250717H — $170,000 fixed price
Category | Count | % of Total
In Scope | 53 | 60%
Scope Creep | 19 | 22%
Borderline | 16 | 18%
Total | 88 | 100%
Key Findings
1. SOW Gap 2 (Sleepover) wording is narrower than initially assumed — 'minimum sleepover top-up' mechanism is IFA-specific and not covered by the gap commitment.
2. The 4 Simplification tickets (PAYM-327–330) represent rework of initial designs that proved unworkable, not refinement — SOW commits to one design-and-build cycle.
3. PAYM-262 (Hibiscus quarterly release) is explicitly excluded by SOW Section 5 Assumption 8: 'future product releases are not included'.
4. PAYM-334 (custom UI widget) has already been built and tested — flag for commercial reconciliation regardless of classification.
5. PAYM-335 may actually be a defect in the dual leave loading configuration (RW says 'pay the higher of the two') rather than a new requirement.

## All Tickets
Ticket | Summary | Type | Status | Priority | Reporter | Assignee | Classification | Source References | Explanation
PAYM-6 | Project Planning | Epic | New | Medium | Karen Mangan | Andrew Humann | In Scope | SOW 3.1; TL 'Original Timeline' — Project Governance row | SOW 3.1 explicitly includes project management activities. Parent epic.
PAYM-8 | Testing | Epic | New | Medium | Karen Mangan | Sameer Gundu | In Scope | SOW 3.5; TL 'Revised PPT' — PPT1/PPT2/PPT3 rows | SOW 3.5 commits to functional testing and parallel runs. Parent epic.
PAYM-9 | Go Live | Epic | New | Medium | Karen Mangan | Heidi Simoniuk | In Scope | SOW 3.7; TL 'Revised PPT' — Go-Live section | SOW 3.7 covers go-live preparation and hypercare. Parent epic.
PAYM-12 | Schedule Reporting Workshop | Task | New | Medium | Karen Mangan | Heidi Simoniuk | In Scope | SOW 3.2; SOW 3.6; RW 'Custom reports and dashboards' (Custom) | Discovery workshop and training on reports/dashboards. RW explicitly calls for user training.
PAYM-45 | Minimum Sleepover is not working as expected | Bug | Open | High | Anita Maehrle | Lennon McGrath | Scope Creep | SOW Gap 2 wording does not cover this | SOW Gap 2 says 'compliance hours at the lower rate'. Minimum sleepover top-up (IFA-specific, PH/Saturday/casual variants) is bespoke business logic well beyond the gap wording.
PAYM-49 | SIT Exit Sign Off | Task | New | Medium | Karen Mangan | Sameer Gundu | In Scope | SOW 3.5; TL 'Original Timeline' — SIT Testing and Sign Off row | Standard testing gate confirming readiness for UAT.
PAYM-53 | REGRESSION Defect Analysis & Reporting | Task | New | Medium | Karen Mangan | Sameer Gundu | In Scope | SOW 3.5; TL 'Revised PPT' — Post PPT defect resolution rows | Regression analysis integral to parallel runs. Timeline schedules defect resolution windows.
PAYM-69 | PPT Run 1 (Historical Closed Period) | Task | New | Medium | Karen Mangan | Sameer Gundu | In Scope | SOW 3.5; TL 'Revised PPT' — PPT1 row; TL 'PPT1-PPT2' sheet | SOW 3.5 commits to parallel run support. ~2,000 SWs, ~7,000 bookings.
PAYM-70 | PPT2 Run 2 (Current Open Period) | Task | New | Medium | Karen Mangan | Sameer Gundu | In Scope | SOW 3.5; TL 'Revised PPT' — PPT2 row; TL 'PPT1-PPT2' sheet | Second parallel run using current open period in production.
PAYM-71 | PPT Run 3 (Cutover Simulation) | Task | New | Medium | Karen Mangan | Sameer Gundu | In Scope | SOW 3.5; TL 'Revised PPT' — PPT3 row | Final parallel run before go-live (cutover simulation).
PAYM-72 | PPT Reconciliation and Variance Analysis | Task | New | Medium | Karen Mangan | Sameer Gundu | In Scope | SOW 3.5; RW 'Parallel runs & validation' (Standard); TL 'Revised PPT' — reconciliation row | Core purpose of parallel runs. RW calls for comparing 2c9 vs current payroll.
PAYM-73 | PPT Defect Resolution & Re Runs | Task | New | Medium | Karen Mangan | Sameer Gundu | In Scope | SOW 3.5; TL 'Revised PPT' — Post PPT1/PPT2 defect resolution rows | Defect resolution between parallel runs with target completion dates.
PAYM-74 | PPT Exit Sign Off | Task | New | Medium | Karen Mangan | Sameer Gundu | In Scope | SOW 3.5; TL 'Revised PPT' — Go/No-go decision rows | Formal gate confirming parallel testing complete and system ready for go-live.
PAYM-80 | Delivery of Training | Task | In Review | Medium | Karen Mangan | Andrew Humann | In Scope | SOW 3.6; SOW Section 4 Deliverables; TL 'Revised PPT' — PAYM-80 row | SOW 3.6 commits to in-person end-user sessions. Timeline references ticket by number.
PAYM-87 | PIA Privacy Assessment for 2c9 | Task | Open | Medium | Karen Mangan | Paul Joseph | In Scope | SOW Appendix A — Security Deliverables; RW 'Roles and permissions' (Standard) | SOW Appendix A commits to security activities including secure configuration baselines.
PAYM-90 | Support Model Approach and Sign Off | Task | Blocked | Medium | Karen Mangan | Paul Joseph | In Scope | SOW 3.7; TL 'Original Timeline' — Support/Operating Model row | SOW 3.7 covers post go-live support. Timeline includes formal sign-off milestone.
PAYM-91 | Support Model Content and Sign Off | Task | New | Medium | Karen Mangan | Paul Joseph | In Scope | SOW 3.7; TL 'Original Timeline' — Support Model Content row | Content deliverable accompanying PAYM-90. Timeline includes separate sign-off milestone.
PAYM-92 | PPT Portal Access & Review | Task | In Review | Medium | Karen Mangan | Heidi Simoniuk | In Scope | RW 'Employee portal capabilities' (Standard); DW 'EMPLOYEE & APPROVER PORTAL' sheet | Portal is Standard in RW. Portal access needed for PPT testing of leave/PH workflows.
PAYM-98 | Finance GL Report Build — Location requirements | Task | Open | Medium | Karen Mangan | Julian McGrath | Scope Creep | Not in SOW, RW, or DW | Dual-location columns (primary + service delivery) on GL report is a custom reporting enhancement not identified during discovery.
PAYM-112 | [Test] Bank ABA File | Story | In Review | Medium | Karen Mangan | Heidi Simoniuk | In Scope | SOW 3.3; RW 'Master payroll data setup' (Standard); TL — Build 2 row; DW 'PAYMENT ENTITY' sheet | Bank ABA file is standard payroll output. Timeline lists it as specific build item.
PAYM-113 | [Test] Super Clearing File | Story | In Review | Medium | Karen Mangan | Heidi Simoniuk | In Scope | SOW 3.3; RW 'Stapled super' (Custom); TL — Build 3 row; DW 'DEFAULT SUPERANNUATION' sheet | Super clearing house file is standard payroll integration. Timeline lists as build item.
PAYM-114 | [Test] ATO Integration | Story | New | Medium | Karen Mangan | Heidi Simoniuk | In Scope | SOW 3.3; TL 'Original Timeline' — Build 4 row | ATO/STP integration is standard payroll compliance. Timeline lists as build item.
PAYM-115 | [Test] GL Integration (Netsuite) | Story | New | Medium | Karen Mangan | Heidi Simoniuk | In Scope | SOW 3.3 ('GL and cost code set up … export files to Netsuite'); TL — Build 5 row | SOW 3.3 explicitly names GL integration with Netsuite.
PAYM-121 | Build Integration — Project Evolution CR1 changes | Story | In Review | Medium | Karen Mangan | Julian McGrath | In Scope | RW-PE 'Project Evolution' sheet; TL — Build 11 row ('CR1 SO'); RAID R01 | CR1 formally approved as Change Request. Timeline records sign-off. RAID tracks as approved.
PAYM-123 | SACS Project Codes | Task | Open | Low | Karen Mangan | Lennon McGrath | In Scope | RW 'Short shift and penalty pay codes' (Custom); SOW Section 4 Gap 7 | SACS project codes (2.1, 2.2, 2.3) enable manual override. RW includes Custom user story.
PAYM-137 | Community Portal approvers & Payroll system users | Task | Open | Medium | Karen Mangan | Julian McGrath | In Scope | RW 'Employee portal capabilities' (Standard); RW 'Roles and permissions' (Standard); DW 'SYSTEM USERS' sheet | Portal and permission roles are Standard in RW. DW has System Users sheet.
PAYM-145 | Discuss change of State and LSL | Task | Open | Medium | Karen Mangan | Julian McGrath | In Scope | SOW 3.2 (Discovery); RW 'Dual leave loading' (Standard); DW 'LEAVE RULES' sheet | Discovery activity — understanding how state changes impact LSL accrual.
PAYM-151 | [Action AC073] Friday Booking reconciliation report | Task | Open | Medium | Karen Mangan | Julian McGrath | Borderline | RW 'Custom reports and dashboards' — self-service training, not 2c9 build | Could be handled as a training outcome (Hireup builds it themselves after PAYM-299 training). If asking 2c9 to build it, that's additional work.
PAYM-152 | [Action AC076] Sleepover Timing — Hireup internal changes | Task | New | Low | Karen Mangan | Heidi Simoniuk | In Scope | SOW Section 4 Gap 2; SOW 3.1 (Project Management) | Tracks dependencies and timing for sleepover build. Project management under SOW 3.1.
PAYM-159 | Setup custom fields for Portable LSL Registration | Task | Open | Low | Heidi Simoniuk | Julian McGrath | Scope Creep | Not in SOW, RW, or DW | Portable LSL not in any scope document. New compliance stream requiring custom SF fields.
PAYM-166 | [Nice to have] Slack integration for Payroll alerts | Task | New | Medium | Heidi Simoniuk | Alex Luca | Scope Creep | Not in SOW, RW, or DW | No scope document mentions Slack integration. Explicitly tagged 'Nice to have'.
PAYM-167 | Hireup custom Payslip template | Task | In Review | High | Heidi Simoniuk | Julian McGrath | In Scope | SOW Section 4 Gap 7; SOW Deliverables (UI customisation); RW 'Consolidated pay advice' (Custom) | SOW Gap 7 requires payslips to display all-inclusive rate. RW has Custom user story.
PAYM-172 | Include late approvals in Pay Batch [Training] | Task | Open | Medium | Heidi Simoniuk | Andrew Humann | In Scope | SOW 3.6; RW 'Off-cycle pays' (Standard); TL — PAYM-172 + PAYM-207 row | Training on late-approved bookings. RW includes off-cycle pays as Standard. Timeline references ticket.
PAYM-173 | Complete Portable LSL Workbook | Task | Open | Medium | Heidi Simoniuk | Julian McGrath | Scope Creep | Not in SOW, RW, or DW | Portable LSL not in any scope document. Entire workbook for new compliance stream.
PAYM-174 | Sleepover Timing — FairWork award changes | Task | New | Low | Heidi Simoniuk | Heidi Simoniuk | In Scope | SOW 3.1 (Project Management); SOW 3.2 (SCHADS interpretation); RAID risks | Tracking/awareness item only — no build requested. Standard project governance under SOW 3.1.
PAYM-183 | Broken shift & Sleepover bookings incorrect | Bug | In Progress | High | Heidi Simoniuk | Heidi Simoniuk | In Scope | SOW Section 4 Gap 2 + Gap 3; RW 'Broken shift logic' (Standard); RW 'Sleepovers' (Custom) | Spans two SOW gap deliverables. System not recognising broken shifts or applying correct allowances.
PAYM-187 | Sleepover Midday Validation | Task | Open | Medium | Heidi Simoniuk | Lennon McGrath | Borderline | SOW Section 4 Gap 2; RW 'Sleepovers' (Custom) | Validation blocks sleepover approval at midday. Fixing validation is config, but underlying system constraint may require architectural change.
PAYM-193 | Comms to Business to approve retros/tidy data | Task | New | Medium | Karen Mangan | Paul Joseph | In Scope | SOW 3.7 (Go-Live Preparation); RW 'Payroll cutoff and approval workflow' (Standard) | Go-live preparation. Auto-approving outstanding bookings to reduce cutover volumes.
PAYM-194 | Pay batch creation / automation | Story | In Review | Medium | Heidi Simoniuk | Julian McGrath | In Scope | SOW Section 4 Flame Trees; SOW Section 5 Assumption 8; RW 'API-triggered pay batches' + 'Pay batch triggering' + 'Large pay batch processing' (all Custom) | SOW explicitly lists as Flame Trees deliverable. Three separate RW user stories. Most documented in-scope item.
PAYM-207 | Determine best way to enter On-call Allowances | Task | Open | Medium | Karen Mangan | Lennon McGrath | In Scope | SOW 3.3; DW 'ALLOWANCE PAY CODES' + 'ALLOWANCES' sheets; TL — PAYM-172 + PAYM-207 row | On-call allowances in DW. Configuration decision under SOW 3.3. Timeline references ticket.
PAYM-214 | Test PPT Work schedules and minimum hours | Task | Blocked | Medium | Heidi Simoniuk | Sameer Gundu | In Scope | SOW 3.5; RW 'Payroll calendar and cut-off' (Standard); DW 'PAY SCHEDULES & CALENDARS' sheet | Functional testing activity within SOW 3.5. DW captures pay schedule configuration.
PAYM-217 | Review licences and allocations for Hireup resources | Task | New | Medium | Karen Mangan | Paul Joseph | In Scope | SOW 3.1 (resource planning); SOW 3.7 (Go-Live Preparation); DW 'SYSTEM USERS' sheet | Standard project governance and go-live readiness. DW captures system user requirements.
PAYM-219 | Finalise Public holiday calendars and maintenance | Task | In Review | Medium | Heidi Simoniuk | Heidi Simoniuk | In Scope | SOW Section 4 Flame Trees (PH Trigger); RW 'Public holiday by shift location' (Custom); DW 'HU PUBLIC HOLIDAY CAL' + 'PUBLIC HOLIDAYS' sheets | PH Trigger is Flame Trees deliverable. RW requires location-based PH logic. DW has two PH sheets.
PAYM-220 | Confirmation of retro approach — paper to ELT | Task | Open | Medium | Karen Mangan | Paul Joseph | In Scope | SOW 3.7 (Go-Live Preparation); SOW 3.1 (Proactive project management) | Go-live preparation governance. Cutover plan must define retro handling across old/new systems.
PAYM-221 | Audit log requirements | Task | In Review | Medium | Heidi Simoniuk | Heidi Simoniuk | In Scope | RW 'Audit history tracking' (Standard); SOW Appendix A — Security; TL — PAYM-221 row | RW classifies as Standard. SOW Appendix A commits to security logging. Timeline references ticket.
PAYM-229 | Sync Data from 2c9 to Platform | Epic | New | Medium | Heidi Simoniuk | Anita Maehrle | In Scope | RW 'Outbound pay results' (Standard); RW 'Return of pay results' (Custom); TL — Build 10 row; SOW 3.8 | RW has Standard and Custom user stories. Timeline lists as build item 10.
PAYM-232 | Auto-approve workflow for open timesheets | Story | New | Medium | Alex Luca | Swaroop Sridhara | Borderline | RW 'Payroll cutoff and approval workflow' (Standard); RW 'Pay batch triggering' (Custom) | RW says 'define and enforce cutoff process'. Auto-approval is custom scheduled automation beyond standard cutoff configuration. The need arises from in-scope cutoff workflow but the implementation is custom.
PAYM-233 | Configure PROD Instance | Epic | In Review | Medium | Heidi Simoniuk | Julian McGrath | In Scope | SOW 3.3; TL 'Revised PPT' — production uplift rows | SOW 3.3 covers installation and configuration. Timeline schedules production uplift.
PAYM-234 | SCHADS Award rules build | Epic | Open | High | Heidi Simoniuk | Lennon McGrath | In Scope | SOW 3.2 (SCHADS MA000100); SOW 3.3; RW 10+ interpretation user stories; DW 'MA000100 SCHADS' sheet | SOW 3.2 specifically names SCHADS. SOW 3.3 says 'Award Interpretation as per Discovery Workbook'.
PAYM-235 | Configure Payroll engine | Epic | In Review | High | Heidi Simoniuk | Julian McGrath | In Scope | SOW 3.3; RW multiple payroll user stories; DW 'PAYMENT ENTITY', 'PAY SCHEDULES', 'EARNER TYPE', 'LEAVE RULES', 'CALCULATION OF RATES' sheets | SOW 3.3 covers payroll installation and configuration. Parent epic for all payroll engine config.
PAYM-241 | Build Portable LSL Reports (5 states) | Task | Open | Medium | Heidi Simoniuk | Julian McGrath | Scope Creep | Not in SOW, RW, or DW | Portable LSL not in any scope document. 5 state-specific compliance reports — significant build effort.
PAYM-242 | Configure protected earnings (child support, garnishee) | Task | In Review | Medium | Heidi Simoniuk | Julian McGrath | In Scope | SOW 3.3; DW 'DEDUCTION PAY CODES' sheet; RW 'Master payroll data setup' (Standard) | Standard payroll deduction configuration. DW includes Deduction Pay Codes sheet.
PAYM-243 | [UAT] Test Project Evolution CR Changes | Task | New | Medium | Heidi Simoniuk | Sameer Gundu | In Scope | SOW 3.5; RW-PE 'Project Evolution' sheet; TL — Build 11 ('CR1 SO'); RAID R01 | Testing of formally approved CR1. RAID states 'testing will confirm if Risk is abated'.
PAYM-255 | Post Go Live items | Epic | New | Medium | Heidi Simoniuk | Heidi Simoniuk | In Scope | SOW 3.7; TL 'Revised PPT' — Post Go-Live Activities section | SOW 3.7 includes hypercare and post go-live support. Parent epic.
PAYM-261 | End User Training | Epic | New | Medium | Heidi Simoniuk | Andrew Humann | In Scope | SOW 3.6; TL 'Revised PPT' — Training section | SOW 3.6 commits to end-user and administrator training. Parent epic.
PAYM-262 | Quarterly Release — Hibiscus | Story | New | Medium | Heidi Simoniuk | Guy Baxter | Scope Creep | SOW Section 5 Assumption 8 explicitly excludes future product releases | SOW Section 5: 'future product releases are not included'. Hibiscus is a future release. Ticket itself says 'not a must have'. Any work should be a Change Request.
PAYM-271 | Solution for PPT Min Contracted Hours | Task | Open | Medium | Heidi Simoniuk | Julian McGrath | Scope Creep | Not in SOW, RW, or DW | Custom solution for work schedules and automatic minimum hours top-up. JIRA comments acknowledge 'most likely will be a change request'.
PAYM-272 | Solution for Sleepover bookings that cross midday | Task | New | Medium | Heidi Simoniuk | Lennon McGrath | Borderline | SOW Section 4 Gap 2; RW 'Sleepovers' (Custom) | Sleepovers in scope but ticket calls for 'longer term' architectural solution beyond interim workaround. Interim workaround closer to in-scope; permanent product change is scope creep.
PAYM-273 | Sleepover — incorrect payment first & active hours | Bug | Open | High | Alex Luca | Sameer Gundu | Borderline | SOW Section 4 Gap 2; RW 'Sleepovers and disturbances' (Custom) | Base negative-hours bug is arguably a config defect (in scope), but ticket expanded to midnight-crossing active hour calculations beyond basic configuration.
PAYM-278 | Payee Exit, GL, STP [Training] | Task | Open | Medium | Andrew Humann | Heidi Simoniuk | In Scope | SOW 3.6; TL 'Revised PPT' — PAYM-278 row | 2-hour training on payee terminations, GL, STP, super. Timeline references ticket by number.
PAYM-279 | Process for FDVL & Pay advices | Task | Open | Medium | Heidi Simoniuk | Julian McGrath | Scope Creep | Not in SOW, RW, or DW | FDVL not in any scope document. Pay advice suppression per legislation is a specific compliance requirement not identified in discovery.
PAYM-280 | Process to create new pay codes & ensure rates generated | Task | New | Medium | Heidi Simoniuk | Lennon McGrath | Scope Creep | Not in SOW, RW, or DW | Operational documentation and Apex job tooling for ongoing BAU activities post-implementation. Beyond SOW handover scope.
PAYM-281 | Define template for data load of leave balances | Task | In Review | Medium | Heidi Simoniuk | Heidi Simoniuk | In Scope | SOW 3.4 ('Templates provided by 2cloudnine'); DW 'LEAVE RULES' sheet | SOW 3.4 explicitly offers templates as a migration method. Direct deliverable.
PAYM-293 | Pay trans import defaulting to $34.59 | Bug | In Progress | High | Sameer Gundu | Heidi Simoniuk | Borderline | SOW 3.3; TL — Build 8 row (Transaction Import Files) | Import bug (defaulting to wrong rate) is in scope as a config defect in Build 8. But ticket conflates this with CAG/PPL rate requirements (PAYM-311, itself out of scope).
PAYM-294 | Public holidays incorrectly tagged (UX Issue) | Bug | In Progress | Low | Heidi Simoniuk | Guy Baxter | In Scope | SOW Section 4 Flame Trees (PH Trigger); RW 'Public holiday by shift location' (Custom); DW 'HU PUBLIC HOLIDAY CAL' sheet | PH calendar defect. PH Trigger is Flame Trees deliverable. RW and DW document PH requirements.
PAYM-296 | SACS Short shifts calcs incorrect | Bug | In Progress | High | Heidi Simoniuk | Jacqui Fenton | In Scope | SOW Section 4 Gap 6; RW 'Short shift detection and uplift' + 'Short shift uplift' (both Custom) | SOW Gap 6 lists short shifts. SACS short shifts not paying 2hr × base rate is a failure in the gap deliverable.
PAYM-299 | Reports and Dashboard, Portal [Training] | Task | Open | Medium | Andrew Humann | Heidi Simoniuk | In Scope | SOW 3.6; RW 'Standard payroll reports' + 'Custom reports and dashboards'; RW 'Employee portal capabilities' (Standard) | Training on reports, dashboards, portal. RW calls for 'training for key Hireup users on report and dashboard creation'.
PAYM-301 | Investigate Error Log for Bulk Approval | Task | New | Medium | Alex Luca | Alex Luca | In Scope | SOW 3.5 (testing assistance); SOW 3.8 (ad hoc support) | Error during bulk approval needing investigation. Standard defect triage during testing.
PAYM-310 | Public holiday part day — Afternoon shift not recognised | Task | Open | Medium | Heidi Simoniuk | Heidi Simoniuk | In Scope | SOW Section 4 Flame Trees (PH Trigger); RW 'Public holiday by shift location' (Custom); DW 'HU PUBLIC HOLIDAY CAL' sheet | Part-day PH not recognised for afternoon shifts. PH Trigger is Flame Trees deliverable.
PAYM-311 | Default pay rates for CAG & PPL | Task | In Review | High | Heidi Simoniuk | Heidi Simoniuk | Borderline | Partially — SOW 3.3 covers pay code config; DW does not list CAG/PPL explicitly | Mirrors PAYM-293 pattern (import defaulting incorrectly). Config is standard but CAG/PPL pay categories were not in Discovery Workbook.
PAYM-312 | Sleepovers > 18 hours in duration incorrect | Bug | In Progress | High | Heidi Simoniuk | Lennon McGrath | Scope Creep | SOW Gap 2 wording does not cover this | 18+ hour sleepovers spanning multiple calendar days with daily OT resets and cascading penalty rates is complex engine work — not 'configuring compliance hours at the lower rate'.
PAYM-313 | Sleepovers > 18 hours & back to back Sleepovers | Bug | In Progress | High | Heidi Simoniuk | Lennon McGrath | Scope Creep | SOW Gap 2 wording does not cover this | Back-to-back sleepovers across three calendar days with consecutive OT resets. Even further beyond Gap 2 than PAYM-312.
PAYM-314 | Daily OT Calc incorrect | Bug | Open | High | Heidi Simoniuk | Lennon McGrath | In Scope | SOW Section 4 Gap 1 ('bookings crossing midnight … wrongly interpreted'); RW 'Overnight shift logic' (Custom) | Overnight shift (11pm-7am) exactly matches SOW Gap 1 scenario — starts weekday, crosses midnight, ends after 6am.
PAYM-318 | Short Shift Saturday & PH payment incorrect — Inflated | Bug | Open | High | Heidi Simoniuk | Lennon McGrath | In Scope | SOW Section 4 Gap 6; RW 'Short shift detection and uplift' (Custom) | Defect in short shift logic. SOW Gap 6 commits to short shifts. System over-calculating violates RW 'pay the higher of' rule.
PAYM-319 | Minimum Sleepover Rates incorrect | Bug | Open | High | Heidi Simoniuk | Lennon McGrath | Scope Creep | SOW Gap 2 wording does not cover this | 'Minimum sleepover top-up' with day-type-specific rates (PH $87.03, weekday Night $44.64) is a concept not in SOW or RW.
PAYM-324 | Daily OT not triggered with Day booking + Sleepover | Bug | In Progress | High | Heidi Simoniuk | Heidi Simoniuk | Scope Creep | SOW Gap 2 wording does not cover this | Fundamentally an OT aggregation issue, not sleepover configuration. The sleepover is incidental — the bug is that daily OT doesn't aggregate across booking types.
PAYM-325 | Sleepover crossing midday paying incorrect shift penalty | Bug | Open | Medium | Heidi Simoniuk | Jacqui Fenton | Scope Creep | SOW Gap 2 wording does not cover this | Penalty rate classification at midday boundaries is a system constraint workaround, not sleepover compliance-hour configuration.
PAYM-326 | Create new pay code — Min Sleepover Mon-Fri | Task | In Review | High | Heidi Simoniuk | Heidi Simoniuk | Scope Creep | SOW Gap 2 wording does not cover this | New pay code for minimum sleepover top-up mechanism (itself not in SOW). Day-type variant splitting is net new configuration.
PAYM-327 | [Simplification 1] Consolidate Pay Code Structure | Task | In Review | High | Andrew Humann | Lennon McGrath | Borderline | Partially — RW 'Short shift and penalty pay codes' says 'rationalise names'; SOW 3.3 | Systemic architecture rework exceeds the RW 'rationalise pay code names' user story. Changing the reporting model is not initial configuration — it is re-architecture.
PAYM-328 | [Simplification 2] Decouple Sleepover & Remote Work from Broken Shift | Task | In Review | Medium | Andrew Humann | Heidi Simoniuk | Borderline | Partially — SOW Section 4 Gaps 2, 3; RW 'Broken shift logic' + 'Sleepovers' | Rework of a design that proved unworkable. Hireup requested coupling, 2c9 built it, now being unwound. SOW commits to one build cycle, not iterative redesigns.
PAYM-329 | [Simplification 3] Standardise Discretionary Allowance | Task | In Review | Medium | Andrew Humann | Heidi Simoniuk | Borderline | Partially — SOW Section 4 Gap 7 | Second iteration of SOW Gap 7 deliverable. First implementation introduced 'non-standard logic prone to errors' — this is a redesign, not a refinement.
PAYM-330 | [Simplification 4] Review and Standardise Broken/Split Shift Logic | Task | In Review | Medium | Andrew Humann | Heidi Simoniuk | Borderline | Partially — SOW Section 4 Gaps 3, 4, 6; RW broken shift + short shift stories | Rework of Gaps 3/4/6 due to design complexity. Original build created 'custom logic and configuration complexity' that now needs simplifying.
PAYM-333 | Review Apex code / Changes to flows impacts | Task | New | Medium | Heidi Simoniuk | Lennon McGrath | Scope Creep | Not in SOW, RW, or DW | Code audit with maintenance impact assessment. SOW covers training/handover, not auditing codebase.
PAYM-334 | Create UI Widget for adhoc timesheet entries | Task | New | Medium | Heidi Simoniuk | Sameer Gundu | Scope Creep | Not in SOW, RW, or DW | Custom Salesforce LWC development — not 'configuration'. Integration assumes timesheets from Hireup Platform. NOTE: widget already built per JIRA comments — flag for commercial reconciliation.
PAYM-335 | Investigate adjustments for Payee leave events | Task | In Review | Medium | Heidi Simoniuk | Julian McGrath | Borderline | Partially — RW 'Dual leave loading' (Standard) says 'pay the higher of the two' | System defaulting to 17.5% instead of higher weekend rate may be a config defect in dual leave loading (RW says 'pay the higher'). Override request is a workaround for the underlying issue.
PAYM-336 | Picklist of Allowance pay codes | Task | In Review | Medium | Heidi Simoniuk | Lennon McGrath | In Scope | SOW 3.3; SOW Deliverables (UI customisation); DW 'ALLOWANCE PAY CODES' sheet | Standard Salesforce picklist configuration. DW documents which allowance codes to include.
PAYM-337 | Hireup custom Payslip Email body | Task | Open | High | Heidi Simoniuk | Julian McGrath | Borderline | Partially — SOW Section 4 Gap 7 covers payslip content; SOW Deliverables (UI/terminology) | Email body is the delivery wrapper for the in-scope custom payslip (PAYM-167). Straightforward text config, but legal disclaimers and branding push it beyond simple configuration.
PAYM-340 | End of year processing [Support/Training] | Task | New | Medium | Andrew Humann | Andrew Humann | In Scope | SOW 3.6; SOW 3.7 (post go-live support) | EOFY processing training is standard payroll. Aligns with SOW 3.6 training and 3.7 support transition.
PAYM-341 | Production User Review | Task | In Review | Medium | Guy Baxter | Paul Joseph | In Scope | SOW 3.7; SOW Appendix A — Security (least privilege, access reviews); DW 'SYSTEM USERS' sheet | Go-live readiness (SOW 3.7) and security obligation (Appendix A). DW documents user list.
PAYM-342 | Align on Reversed Transactions display on Pay Advice | Task | In Review | Medium | Alex Luca | Julian McGrath | Borderline | Partially — SOW Section 4 Gap 5 (consolidated payslips); RW 'Consolidated pay advice' (Custom) | Gap 5 commits to consolidation, not redesigning reversal display. Display alignment is new UX requirement; rates/PAYG issues within the ticket are genuine defects.
PAYM-344 | Public holiday under paid of SW L1 | Bug | New | High | Sameer Gundu | Jacqui Fenton | In Scope | SOW Section 4 Flame Trees (PH Trigger); SOW 3.3 | PH underpayment is a rate calculation defect. PH Trigger is Flame Trees deliverable. Correct PH rates are fundamental to SCHADS.
PAYM-345 | Update missing BSBs in Prod | Bug | Open | Medium | Heidi Simoniuk | Julian McGrath | In Scope | SOW 3.3; RW 'Master payroll data setup' (Standard) | BSB data integrity essential for Bank ABA payments. RW calls for validating master data prior to go-live.
PAYM-347 | Update MV Allowance to $1.04 per KM | Task | In Review | High | Heidi Simoniuk | Sameer Gundu | Borderline | SOW 3.3; DW 'ALLOWANCE PAY CODES' + 'ALLOWANCES' sheets | Discretionary business rate change (Hireup chose to increase by 5c), not a defect or regulatory requirement. Trivial effort but sets a precedent for mid-project changes.
PAYM-351 | Submitting Leave fails — EmailException error | Task | Open | Medium | Alex Luca | Alex Luca | In Scope | RW 'Employee portal capabilities' (Standard); SOW 3.3 | Portal is Standard in RW. Leave submission failing due to trigger exception is a product defect.
PAYM-354 | Production Org API Limits | Task | Open | Medium | Guy Baxter | Alex Luca | Scope Creep | Not in SOW, RW, or DW | Ongoing operational monitoring of production API consumption. Not a configuration or build task.
PAYM-356 | New Training pay code does not have associated pay rate | Bug | New | Medium | Heidi Simoniuk | Lennon McGrath | In Scope | SOW 3.3; RW 'Short shift and penalty pay codes' (Custom) | Pay code producing $0 payments due to missing rate is a configuration defect.
PAYM-357 | Review and check GL Account codes | Task | New | Medium | Heidi Simoniuk | Julian McGrath | In Scope | SOW 3.3 ('GL and cost code set up … export files to Netsuite') | SOW 3.3 explicitly includes GL setup. Validating GL mappings is standard QA before go-live.
PAYM-358 | Separate pay code for Training (GL 50710 / 50720) | Task | New | High | Sameer Gundu | Jacqui Fenton | Borderline | Partially — RW 'Remote work and training' (Custom) requires 'dedicated codes'; GL mapping is the extension | RW requires 'dedicated codes from the core system' for training. Pay code creation is covered; specific GL account mapping (50710/50720) is the borderline extension.

## Scope Creep
# | Ticket | Summary | Reporter | Source References | Explanation
1 | PAYM-45 | Minimum Sleepover is not working as expected | Anita Maehrle | SOW Gap 2 wording does not cover this | SOW Gap 2 says 'compliance hours at the lower rate'. Minimum sleepover top-up (IFA-specific, PH/Saturday/casual variants) is bespoke business logic well beyond the gap wording.
2 | PAYM-98 | Finance GL Report Build — Location requirements | Karen Mangan | Not in SOW, RW, or DW | Dual-location columns (primary + service delivery) on GL report is a custom reporting enhancement not identified during discovery.
3 | PAYM-159 | Setup custom fields for Portable LSL Registration | Heidi Simoniuk | Not in SOW, RW, or DW | Portable LSL not in any scope document. New compliance stream requiring custom SF fields.
4 | PAYM-166 | [Nice to have] Slack integration for Payroll alerts | Heidi Simoniuk | Not in SOW, RW, or DW | No scope document mentions Slack integration. Explicitly tagged 'Nice to have'.
5 | PAYM-173 | Complete Portable LSL Workbook | Heidi Simoniuk | Not in SOW, RW, or DW | Portable LSL not in any scope document. Entire workbook for new compliance stream.
6 | PAYM-241 | Build Portable LSL Reports (5 states) | Heidi Simoniuk | Not in SOW, RW, or DW | Portable LSL not in any scope document. 5 state-specific compliance reports — significant build effort.
7 | PAYM-262 | Quarterly Release — Hibiscus | Heidi Simoniuk | SOW Section 5 Assumption 8 explicitly excludes future product releases | SOW Section 5: 'future product releases are not included'. Hibiscus is a future release. Ticket itself says 'not a must have'. Any work should be a Change Request.
8 | PAYM-271 | Solution for PPT Min Contracted Hours | Heidi Simoniuk | Not in SOW, RW, or DW | Custom solution for work schedules and automatic minimum hours top-up. JIRA comments acknowledge 'most likely will be a change request'.
9 | PAYM-279 | Process for FDVL & Pay advices | Heidi Simoniuk | Not in SOW, RW, or DW | FDVL not in any scope document. Pay advice suppression per legislation is a specific compliance requirement not identified in discovery.
10 | PAYM-280 | Process to create new pay codes & ensure rates generated | Heidi Simoniuk | Not in SOW, RW, or DW | Operational documentation and Apex job tooling for ongoing BAU activities post-implementation. Beyond SOW handover scope.
11 | PAYM-312 | Sleepovers > 18 hours in duration incorrect | Heidi Simoniuk | SOW Gap 2 wording does not cover this | 18+ hour sleepovers spanning multiple calendar days with daily OT resets and cascading penalty rates is complex engine work — not 'configuring compliance hours at the lower rate'.
12 | PAYM-313 | Sleepovers > 18 hours & back to back Sleepovers | Heidi Simoniuk | SOW Gap 2 wording does not cover this | Back-to-back sleepovers across three calendar days with consecutive OT resets. Even further beyond Gap 2 than PAYM-312.
13 | PAYM-319 | Minimum Sleepover Rates incorrect | Heidi Simoniuk | SOW Gap 2 wording does not cover this | 'Minimum sleepover top-up' with day-type-specific rates (PH $87.03, weekday Night $44.64) is a concept not in SOW or RW.
14 | PAYM-324 | Daily OT not triggered with Day booking + Sleepover | Heidi Simoniuk | SOW Gap 2 wording does not cover this | Fundamentally an OT aggregation issue, not sleepover configuration. The sleepover is incidental — the bug is that daily OT doesn't aggregate across booking types.
15 | PAYM-325 | Sleepover crossing midday paying incorrect shift penalty | Heidi Simoniuk | SOW Gap 2 wording does not cover this | Penalty rate classification at midday boundaries is a system constraint workaround, not sleepover compliance-hour configuration.
16 | PAYM-326 | Create new pay code — Min Sleepover Mon-Fri | Heidi Simoniuk | SOW Gap 2 wording does not cover this | New pay code for minimum sleepover top-up mechanism (itself not in SOW). Day-type variant splitting is net new configuration.
17 | PAYM-333 | Review Apex code / Changes to flows impacts | Heidi Simoniuk | Not in SOW, RW, or DW | Code audit with maintenance impact assessment. SOW covers training/handover, not auditing codebase.
18 | PAYM-334 | Create UI Widget for adhoc timesheet entries | Heidi Simoniuk | Not in SOW, RW, or DW | Custom Salesforce LWC development — not 'configuration'. Integration assumes timesheets from Hireup Platform. NOTE: widget already built per JIRA comments — flag for commercial reconciliation.
19 | PAYM-354 | Production Org API Limits | Guy Baxter | Not in SOW, RW, or DW | Ongoing operational monitoring of production API consumption. Not a configuration or build task.

## Borderline
# | Ticket | Summary | Reporter | Source References | Explanation
1 | PAYM-151 | [Action AC073] Friday Booking reconciliation report | Karen Mangan | RW 'Custom reports and dashboards' — self-service training, not 2c9 build | Could be handled as a training outcome (Hireup builds it themselves after PAYM-299 training). If asking 2c9 to build it, that's additional work.
2 | PAYM-187 | Sleepover Midday Validation | Heidi Simoniuk | SOW Section 4 Gap 2; RW 'Sleepovers' (Custom) | Validation blocks sleepover approval at midday. Fixing validation is config, but underlying system constraint may require architectural change.
3 | PAYM-232 | Auto-approve workflow for open timesheets | Alex Luca | RW 'Payroll cutoff and approval workflow' (Standard); RW 'Pay batch triggering' (Custom) | RW says 'define and enforce cutoff process'. Auto-approval is custom scheduled automation beyond standard cutoff configuration. The need arises from in-scope cutoff workflow but the implementation is custom.
4 | PAYM-272 | Solution for Sleepover bookings that cross midday | Heidi Simoniuk | SOW Section 4 Gap 2; RW 'Sleepovers' (Custom) | Sleepovers in scope but ticket calls for 'longer term' architectural solution beyond interim workaround. Interim workaround closer to in-scope; permanent product change is scope creep.
5 | PAYM-273 | Sleepover — incorrect payment first & active hours | Alex Luca | SOW Section 4 Gap 2; RW 'Sleepovers and disturbances' (Custom) | Base negative-hours bug is arguably a config defect (in scope), but ticket expanded to midnight-crossing active hour calculations beyond basic configuration.
6 | PAYM-293 | Pay trans import defaulting to $34.59 | Sameer Gundu | SOW 3.3; TL — Build 8 row (Transaction Import Files) | Import bug (defaulting to wrong rate) is in scope as a config defect in Build 8. But ticket conflates this with CAG/PPL rate requirements (PAYM-311, itself out of scope).
7 | PAYM-311 | Default pay rates for CAG & PPL | Heidi Simoniuk | Partially — SOW 3.3 covers pay code config; DW does not list CAG/PPL explicitly | Mirrors PAYM-293 pattern (import defaulting incorrectly). Config is standard but CAG/PPL pay categories were not in Discovery Workbook.
8 | PAYM-327 | [Simplification 1] Consolidate Pay Code Structure | Andrew Humann | Partially — RW 'Short shift and penalty pay codes' says 'rationalise names'; SOW 3.3 | Systemic architecture rework exceeds the RW 'rationalise pay code names' user story. Changing the reporting model is not initial configuration — it is re-architecture.
9 | PAYM-328 | [Simplification 2] Decouple Sleepover & Remote Work from Broken Shift | Andrew Humann | Partially — SOW Section 4 Gaps 2, 3; RW 'Broken shift logic' + 'Sleepovers' | Rework of a design that proved unworkable. Hireup requested coupling, 2c9 built it, now being unwound. SOW commits to one build cycle, not iterative redesigns.
10 | PAYM-329 | [Simplification 3] Standardise Discretionary Allowance | Andrew Humann | Partially — SOW Section 4 Gap 7 | Second iteration of SOW Gap 7 deliverable. First implementation introduced 'non-standard logic prone to errors' — this is a redesign, not a refinement.
11 | PAYM-330 | [Simplification 4] Review and Standardise Broken/Split Shift Logic | Andrew Humann | Partially — SOW Section 4 Gaps 3, 4, 6; RW broken shift + short shift stories | Rework of Gaps 3/4/6 due to design complexity. Original build created 'custom logic and configuration complexity' that now needs simplifying.
12 | PAYM-335 | Investigate adjustments for Payee leave events | Heidi Simoniuk | Partially — RW 'Dual leave loading' (Standard) says 'pay the higher of the two' | System defaulting to 17.5% instead of higher weekend rate may be a config defect in dual leave loading (RW says 'pay the higher'). Override request is a workaround for the underlying issue.
13 | PAYM-337 | Hireup custom Payslip Email body | Heidi Simoniuk | Partially — SOW Section 4 Gap 7 covers payslip content; SOW Deliverables (UI/terminology) | Email body is the delivery wrapper for the in-scope custom payslip (PAYM-167). Straightforward text config, but legal disclaimers and branding push it beyond simple configuration.
14 | PAYM-342 | Align on Reversed Transactions display on Pay Advice | Alex Luca | Partially — SOW Section 4 Gap 5 (consolidated payslips); RW 'Consolidated pay advice' (Custom) | Gap 5 commits to consolidation, not redesigning reversal display. Display alignment is new UX requirement; rates/PAYG issues within the ticket are genuine defects.
15 | PAYM-347 | Update MV Allowance to $1.04 per KM | Heidi Simoniuk | SOW 3.3; DW 'ALLOWANCE PAY CODES' + 'ALLOWANCES' sheets | Discretionary business rate change (Hireup chose to increase by 5c), not a defect or regulatory requirement. Trivial effort but sets a precedent for mid-project changes.
16 | PAYM-358 | Separate pay code for Training (GL 50710 / 50720) | Sameer Gundu | Partially — RW 'Remote work and training' (Custom) requires 'dedicated codes'; GL mapping is the extension | RW requires 'dedicated codes from the core system' for training. Pay code creation is covered; specific GL account mapping (50710/50720) is the borderline extension.

## Reclassifications
Ticket | Summary | Original Classification | Revised Classification | Direction | Rationale
PAYM-45 | Minimum Sleepover not working | In Scope | Scope Creep | In Scope → Scope Creep | SOW Gap 2 says 'compliance hours at the lower rate'. Minimum sleepover top-up (IFA-specific) is bespoke logic beyond the gap.
PAYM-262 | Quarterly Release — Hibiscus | In Scope | Scope Creep | In Scope → Scope Creep | SOW Section 5 Assumption 8: 'future product releases are not included'. Unambiguous.
PAYM-312 | Sleepovers > 18 hours incorrect | In Scope | Scope Creep | In Scope → Scope Creep | 18+ hour sleepovers with multi-day OT resets is complex engine work beyond Gap 2.
PAYM-313 | Sleepovers > 18 hours & back to back | In Scope | Scope Creep | In Scope → Scope Creep | Back-to-back sleepovers across three calendar days. Further beyond Gap 2 than PAYM-312.
PAYM-319 | Minimum Sleepover Rates incorrect | In Scope | Scope Creep | In Scope → Scope Creep | 'Minimum sleepover top-up' with day-type rates not in SOW or RW.
PAYM-324 | Daily OT not triggered with Day + Sleepover | In Scope | Scope Creep | In Scope → Scope Creep | OT aggregation issue, not sleepover configuration. Sleepover is incidental.
PAYM-325 | Sleepover crossing midday incorrect penalty | In Scope | Scope Creep | In Scope → Scope Creep | Penalty rate at midday boundaries is system constraint work, not sleepover config.
PAYM-326 | New pay code — Min Sleepover Mon-Fri | In Scope | Scope Creep | In Scope → Scope Creep | New pay code for min sleepover mechanism (itself not in SOW).
PAYM-232 | Auto-approve workflow for timesheets | In Scope | Borderline | In Scope → Borderline | Auto-approval is custom scheduled automation, not standard cutoff configuration.
PAYM-273 | Sleepover incorrect first & active hours | In Scope | Borderline | In Scope → Borderline | Base bug arguably in scope, but expanded to midnight-crossing calculations.
PAYM-293 | Pay trans import defaulting to $34.59 | In Scope | Borderline | In Scope → Borderline | Import bug in scope, but conflates with CAG/PPL requirements (PAYM-311).
PAYM-327 | [Simplification 1] Consolidate Pay Codes | In Scope | Borderline | In Scope → Borderline | Systemic rework exceeds RW 'rationalise names' user story.
PAYM-328 | [Simplification 2] Decouple Sleepover/Broken Shift | In Scope | Borderline | In Scope → Borderline | Rework of design that proved unworkable. SOW commits to one build cycle.
PAYM-329 | [Simplification 3] Standardise Discretionary Allowance | In Scope | Borderline | In Scope → Borderline | Second iteration of Gap 7. First implementation needs redesign.
PAYM-330 | [Simplification 4] Standardise Broken/Split Shift | In Scope | Borderline | In Scope → Borderline | Rework of Gaps 3/4/6 due to design complexity.
PAYM-342 | Reversed Transactions on Pay Advice | In Scope | Borderline | In Scope → Borderline | Gap 5 covers consolidation, not reversal display redesign.
PAYM-347 | Update MV Allowance to $1.04/km | In Scope | Borderline | In Scope → Borderline | Discretionary business rate change, not defect or regulatory.
PAYM-151 | Friday Booking reconciliation report | Scope Creep | Borderline | Scope Creep → Borderline | Could be training outcome — Hireup builds it themselves after PAYM-299 session.
PAYM-311 | Default pay rates for CAG & PPL | Scope Creep | Borderline | Scope Creep → Borderline | Mirrors PAYM-293 import defect pattern. Config is standard but categories not in DW.
PAYM-335 | Investigate adjustments for Payee leave events | Scope Creep | Borderline | Scope Creep → Borderline | RW 'Dual leave loading' says 'pay the higher'. May be a config defect, not new requirement.
PAYM-337 | Custom Payslip Email body | Scope Creep | Borderline | Scope Creep → Borderline | Email is delivery wrapper for in-scope payslip. Legal disclaimers push beyond simple config.
PAYM-358 | Separate Training pay codes (GL 50710/50720) | Scope Creep | Borderline | Scope Creep → Borderline | RW requires 'dedicated codes' for training. GL mapping is the extension.
PAYM-174 | Sleepover Timing — FairWork changes | Borderline | In Scope | Borderline → In Scope | Tracking/awareness only — no build requested. Standard project governance.