## 1. Executive Summary
Hireup SCHADS — CR-Aware Commercial Reconciliation
Project | Hireup Payroll Implementation
SOW Reference | SOW No. 20250717H
SOW Value | $170,000 (fixed price)
Analysis Date | 17 April 2026
Prepared By | 2cloudnine
Review Method | 4-agent independent analysis (CR01, CR02, Project Evolution, Commercial Reconciliation)
Supplements | Hireup Scope Analysis — Finalised.xlsx (97-ticket baseline)
REVISED COMMERCIAL POSITION
CR | Title | Status | Tickets | $ Low | $ High | Priority | Contractual Basis
CR01 | Shift-Level Payroll Tax & FP/NFP Cost Item | Raised 27/11/25 — awaiting signature | Adjacent: 98, 115, 145, 342, 357, 358 | 16000 | 16000 | P0 — sign with carve-out letter | Net-new scope (no ticket coverage). Flat fee. True effort $24k–$30k.
CR02 | Additional Information in Pay Advices | Raised 20/1/26 — REWRITE before signing | PAYM-167, 329, 337, 342, 123 | 6000 | 6000 | P0 — rewrite urgently | Under-priced ($6k vs $15k–$22.5k realistic). 'Discovery under-scoped' language is contractual risk.
CR02-Uplift | CR02 rewrite to realistic T&M | Recommended (not raised) | Same as CR02 | 9000 | 16500 | P1 — bundle with CR02 rewrite | Closes gap to 60–90 hrs. Removes Discovery-fault narrative.
CR-1 | Sleepover Engine Extension | Not raised | PAYM-45, 272, 273, 312, 313, 319, 324, 325, 326 | 20000 | 25000 | P0 — raise before PPT2 | SOW Gap 2 narrow: 'compliance hours at lower rate'. Min top-ups, 18+hr, back-to-back excluded.
CR-2 | Portable LSL Compliance | Not raised | PAYM-159, 173, 241 | 25000 | 35000 | P0 — raise before PPT2 | Zero ambiguity — not in SOW, RW, or DW. Strongest defensibility.
CR-3 | Enhancements & Integrations Bundle | Not raised | PAYM-166, 262, 271, 279, 280, 333, 334, 354 (+ 151/311) | 14000 | 20000 | P1 — raise after CR-1/CR-2 | PAYM-334 already built — reconcile at 50–60% rate.
CR-4 | Project Evolution — Month-End & Audit Trail (NEW) | Not raised — RECOMMENDED | Stages 4–5: month-end recalc, SRO toggle, correction/linkage | 31000 | 50000 | P0 — raise BEFORE Stage 4/5 dev | Dec-2025 design post-dates CR01 (Nov-2025). Emergent post-CR scope.
SUB-TOTAL | Potential recoverable (gross) |  |  | 121000 | 162500
Concessions | Goodwill reapplied (50/50 Simplification + absorb items) |  | PAYM-327/328/330 50/50; 335, 347 absorb | -13000 | -20000 |  | Relationship investment
NET | Net Recoverable Total |  |  | 108000 | 142500 |  | 64–84% of $170k SOW
HEADLINE
Original strategy targeted $46k–$67k recoverable. Post-CR-aware analysis: $108k–$142.5k net recoverable (64–84% of $170k SOW) — contingent on (a) rewriting CR02 this week to remove 'Discovery under-scoped' language, (b) covering-letter carve-out on CR01 before countersignature, (c) raising CR-4 before any Stage 4/5 development begins. The two most load-bearing actions are CR02 rewrite and CR01 covering letter — both this week, before PPT2 gates.

## 2. CR Register
CR ID | Title | Status | Date Raised | Date Signed | $ Low | $ High | Agreed $ | Ticket Count | Priority | Contractual Basis | Notes
CR01 | Shift-Level Payroll Tax & FP/NFP Cost Item | Awaiting signature | 27/11/2025 |  | 16000 | 16000 |  | 0 | P0 | Net-new post-SOW scope. No JIRA ticket coverage in 97-ticket set. | Flat $10k dev + $6k T&M (24 hrs). Under-priced; true effort $24k–$30k. ISSUE COVERING LETTER before countersignature carving out month-end recalc and PAYM-98 GL report.
CR02 | Additional Information in Pay Advices | Awaiting signature — REWRITE FIRST | 20/01/2026 |  | 6000 | 6000 |  | 5 | P0 | Gap 7 rescope + net-new shift-level data sourcing + layout redesign. | $6k for 24 hrs T&M. True effort 60–100 hrs ($15k–$22.5k). 'Significantly more complex than initially identified from Discovery' phrasing is a contractual gift to Hireup — Discovery is 2c9 deliverable (SOW 3.2). REWRITE required.
CR02-Uplift | CR02 rewrite uplift to realistic T&M | Recommended — not raised |  |  | 9000 | 16500 |  | 0 | P1 | Bundled with CR02 rewrite. | Closes gap between raised $6k and realistic $15k–$22.5k. Reframes rationale as 'emergent requirement during build' rather than Discovery failure.
CR-1 | Sleepover Engine Extension | Not raised |  |  | 20000 | 25000 |  | 9 | P0 | SOW Gap 2 ('compliance hours at the lower rate') narrowly worded — excludes min top-ups, 18+hr, back-to-back, midday penalties, OT aggregation. | Raise BEFORE PPT2 completes. Strongest defensibility after CR-2.
CR-2 | Portable LSL Compliance | Not raised |  |  | 25000 | 35000 |  | 3 | P0 | Zero ambiguity — not in SOW, RW, DW, or RAID. | Highest-value CR; zero-risk contractual position. Raise BEFORE PPT2 completes.
CR-3 | Enhancements & Integrations Bundle | Not raised |  |  | 14000 | 20000 |  | 10 | P1 | Mixed scope creep + borderline-CR items. | Negotiation-flex CR. Include PAYM-334 (already built) at 50–60% rate. Offer 10–15% package discount if all CRs approved together.
CR-4 | Project Evolution — Month-End & Audit Trail | NEW — recommended, not raised |  |  | 31000 | 50000 |  | 0 | P0 | Dec-2025 Project Evolution doc introduces Stages 4–5 (month-end recalc engine, SRO Part/All toggle, reversal→correction→linkage audit trail) beyond CR01. | Timing: post-Nov 2025 CR01. 'Emergent post-CR'. Cite SOW §5 Assumption 8 parallel. Raise BEFORE any Stage 4/5 dev starts.

## 3. Ticket–CR Map
Ticket | Summary | Original Class | Revised Class | Assigned CR | Coverage | Confidence | Rationale | Carve-out Flag
PAYM-45 | Minimum Sleepover not working as expected | Scope Creep | Scope Creep | CR-1 | Direct | H | Gap 2 narrow wording — min top-up bespoke to IFA
PAYM-98 | Finance GL Report Build — Location requirements | Scope Creep | Scope Creep (data model via CR01) | CR-4 / CR-3 | Partial | H | CR01 supplies shift-Location data; report build still unfunded | CARVE OUT from CR01
PAYM-159 | Portable LSL custom field requirements | Scope Creep | Scope Creep | CR-2 | Direct | H | Not in SOW/RW/DW
PAYM-166 | Slack integration | Scope Creep | Scope Creep | CR-3 | Direct | H | Tagged 'Nice to have' — outside scope
PAYM-173 | Complete Portable LSL Workbook | Scope Creep | Scope Creep | CR-2 | Direct | H | PLSL compliance stream
PAYM-241 | Portable LSL Reports (5 states) | Scope Creep | Scope Creep | CR-2 | Direct | H | PLSL-specific reporting; not covered by CR02 pay advice work
PAYM-262 | Hibiscus Release adoption | Scope Creep | Scope Creep | CR-3 | Direct | H | SOW §5 Assumption 8 excludes future releases
PAYM-271 | Minimum Contracted Hours (PPT) | Scope Creep | Scope Creep | CR-3 | Direct | H | JIRA comments pre-acknowledge CR
PAYM-279 | FDVL & Pay advices suppression | Scope Creep | Scope Creep | CR-3 | Direct | H | Compliance rule distinct from CR02 display redesign
PAYM-280 | New pay code process tooling | Scope Creep | Scope Creep | CR-3 | Direct | H | Ops tooling outside SOW
PAYM-312 | Sleepover >18hr | Scope Creep | Scope Creep | CR-1 | Direct | H | Gap 2 narrow
PAYM-313 | Sleepover >18hr back-to-back | Scope Creep | Scope Creep | CR-1 | Direct | H | Gap 2 narrow
PAYM-319 | Minimum Sleepover Rates | Scope Creep | Scope Creep | CR-1 | Direct | H | Gap 2 narrow
PAYM-324 | Daily OT Day + Sleepover | Scope Creep | Scope Creep | CR-1 | Direct | H | OT aggregation not in Gap 2
PAYM-325 | Sleepover crossing midday | Scope Creep | Scope Creep | CR-1 | Direct | H | Midday penalty not in Gap 2
PAYM-326 | New pay code Min Sleepover | Scope Creep | Scope Creep | CR-1 | Direct | H | Min top-up pay code bespoke
PAYM-333 | Apex/flow audit | Scope Creep | Scope Creep | CR-3 | Direct | M | Ops monitoring outside SOW
PAYM-334 | Custom UI Widget (already built) | Scope Creep | Scope Creep — reduced rate | CR-3 @ 50–60% | Direct | H | Already consumed effort; first concession
PAYM-354 | Production API Limits monitoring | Scope Creep | Scope Creep | CR-3 | Direct | M | Ops monitoring
PAYM-151 | Friday Booking reconciliation report | Borderline | Borderline → CR | CR-3 | Direct | M | Custom report, not covered by CR01/02
PAYM-232 | Auto-approve workflow | Borderline | Borderline → Negotiate/Absorb | CR-3 or Absorb | Partial | L | Custom scheduled automation; partial scope basis
PAYM-272 | Sleepover midday workaround | Borderline | Borderline → CR (permanent) | CR-1 | Partial | M | Interim in scope; permanent fix is CR-1 territory
PAYM-273 | Sleepover first & active | Borderline | Borderline → CR | CR-1 | Partial | M | Midnight-crossing expansion beyond Gap 1
PAYM-293 | Pay trans $34.59 defect | Borderline | Split — bug absorb; rates CR | Absorb / CR-3 | Partial | M | Defect portion absorb; CAG/PPL rates CR-3
PAYM-311 | CAG/PPL default rates | Borderline | Borderline → CR | CR-3 | Direct | M | Not in DW
PAYM-327 | Simplification 1 — Pay Code | Borderline | Goodwill 50/50 | Shared | Direct | H | SOW commits one build cycle; shared accountability
PAYM-328 | Simplification 2 — Sleepover/Remote | Borderline | Goodwill 50/50 | Shared | Direct | H | Shared accountability
PAYM-329 | Simplification 3 — Discretionary Allowance | Borderline → Absorb | Covered by CR02 | CR02 | Direct | H | Agent B: part of 4-component consolidation
PAYM-330 | Simplification 4 — Broken/Split | Borderline | Goodwill 50/50 | Shared | Direct | H | Shared accountability
PAYM-335 | Leave events adjustments | Borderline | Absorb (likely config defect) | Absorb | Direct | M | Defect territory
PAYM-337 | Custom Payslip Email body | Borderline → CR | Covered by CR02 | CR02 | Partial | M | Email wrapper likely bundled with layout redesign
PAYM-342 | Reversed Transactions on Pay Advice | Borderline → Negotiate | Covered by CR02 (primary) | CR02 + CR01 adjacent | Direct | M | CR02 layout; CR01 reversal mechanism
PAYM-347 | MV Allowance $1.04/km | Borderline → Absorb | Goodwill Absorb | Absorb | Direct | H | Trivial precedent; absorb
PAYM-115 | [Test] GL Integration (Netsuite) | In Scope | In Scope — complexity uplift | CR01 adjacent | Adjacent | M | FP/NFP + reversal journals grow scope | CARVE OUT complexity in CR-4
PAYM-123 | SACS Project Codes | In Scope | In Scope — CR02 adjacent | CR02 adjacent | Adjacent | L | Touches pay-code consolidation
PAYM-145 | Change of State and LSL | In Scope | In Scope — split CR01/CR-2 | CR01 + CR-2 | Partial | M | State changes first-class via CR01; LSL accrual/PLSL linkage to CR-2
PAYM-167 | Hireup custom Payslip template | In Scope (Gap 7) | Covered by CR02 | CR02 | Direct | H | Agent B: CR02 core target
PAYM-357 | Review and check GL Account codes | In Scope | In Scope — CR01 uplift | CR01 adjacent | Adjacent | M | FP/NFP doubles GL surface
PAYM-358 | Training GL split (50710/50720) | Borderline → Negotiate | Covered by CR01 (template) | CR01 adjacent | Partial | M | Dual-cost-item pattern covers

## 4. Commercial Actions
# | Action | Owner | Timing | Status | $ Impact Low | $ Impact High | Dependencies | Notes
1 | Withdraw CR02 draft; rewrite at 60–90 hrs ($15k–$22.5k); strip 'Discovery under-scoped' phrasing | Guy / 2c9 Delivery Lead | This week — before Hireup signs | Open | 9000 | 16500 | None | Reframe as 'emergent requirement during build'
2 | Sign CR01 but issue covering letter carving out (i) month-end recalc, (ii) PAYM-98 GL report build, (iii) SRO Part/All toggle | 2c9 Delivery Lead | Before CR01 countersignature | Open | 31000 | 50000 | CR01 not yet signed | Protects CR-4 position
3 | Raise CR-4 Project Evolution Addendum (Stages 4–5) | Guy + Delivery Lead | Within 2 weeks, before any Stage 4/5 dev | Open | 31000 | 50000 | Action #2 covering letter | Cite Dec-2025 doc post-dates Nov-2025 CR01
4 | Raise CR-1 Sleepover Engine ($20k–$25k) | Account Lead | Within 2 weeks — before PPT2 | Open | 20000 | 25000 | None | SOW Gap 2 narrow citation
5 | Raise CR-2 Portable LSL ($25k–$35k) | Account Lead | Within 2 weeks — before PPT2 | Open | 25000 | 35000 | None | Zero ambiguity — strongest position
6 | Raise CR-3 Enhancements Bundle; PAYM-334 at 50–60% rate | Account Lead | After CR-1/CR-2 lodged | Open | 14000 | 20000 | Actions #4, #5 | Package discount 10–15% if all approved together
7 | Document in writing that CR01's 24hr T&M did NOT cover correction/linkage or month-end recalc | 2c9 Delivery Lead | This week | Open | 0 | 0 | None | Defends CR-4 commercial position
8 | Apply goodwill concessions: 50/50 on PAYM-327/328/330; absorb PAYM-347, 335 | Account Lead | With CR-1/CR-2 lodgement | Open | -13000 | -20000 | Actions #4, #5 | Relationship capital to strengthen CR positions
9 | Reclassify in Finalised sheet: 167, 329, 337, 342 → 'Covered by CR02'; 358 → 'Covered by CR01' | Guy | Within 1 week | Open | 0 | 0 | None | Housekeeping — keep Finalised in sync
10 | Sequence: CR02-rewrite + CR01-letter (now) → CR-1/CR-2 (2 wks) → CR-4 (2–4 wks) → CR-3 (post-PPT2) | Guy + Account Lead | Ongoing | In Progress | 0 | 0 | All | Preserves negotiation leverage

## 5. Risk Register
# | Risk | Severity | Linked CR | Mitigation | Owner | Status | Date Identified
1 | CR02 'more complex than Discovery identified' language — Discovery is 2c9 deliverable (SOW 3.2). Hireup counsel could argue under-estimation is 2c9 risk to absorb. | HIGH | CR02 | Withdraw, rewrite as 'emergent requirement during build'. Never admit Discovery fault in writing. | Guy / Delivery Lead | Open | 17/04/2026
2 | CR02 precedent risk — if Hireup accepts 'Discovery under-scoped' framing, reusable for CR-1/CR-3. If rejected, damages CR-1/CR-3. | HIGH | CR02 → CR-1, CR-3 | Remove phrase entirely. Reserve rescope argument in covering note. | Guy | Open | 17/04/2026
3 | CR01 'journal reversal capability' could be read broadly to subsume Stage 5 correction/linkage and Stage 4 recalc. | HIGH | CR01 / CR-4 | Covering letter NOW: explicit written carve-out of month-end recalc, correction journals, 3-way audit linkage. | Delivery Lead | Open | 17/04/2026
4 | CR01 $16k flat materially under-priced ($24k–$30k true) — sets low-ball precedent. | MED | CR01 | Frame CR-4 as 'uncontemplated by CR01 pricing'; use Agent A effort estimate as benchmark. | Delivery Lead | Open | 17/04/2026
5 | Stages 4/5 drift — Dec-2025 PE doc adds scope Hireup may assume is 'included' since CR01 touched PE. | HIGH | CR01 / CR-4 | CR-4 raised BEFORE any dev. Document Dec-2025 post-dates Nov-2025 CR01. | Guy + Delivery Lead | Open | 17/04/2026
6 | PAYM-334 already built — no commercial mechanism to recover. | MED | CR-3 | Include in CR-3 at 50–60% reduced rate. First concession if negotiation needed. | Account Lead | Open | 17/04/2026
7 | SOW §5 Assumption 8 parallel — excludes Hibiscus AND supports excluding Stages 4/5 (positive risk). | LOW | CR-3 / CR-4 | Cite explicitly in CR-4 and CR-3 cover notes. | Guy | Mitigated | 17/04/2026
8 | Gap 7 own-mouth admission via CR02 — '2c9 said on paper' that Gap 7 was under-specified. | MED | CR02 | Reframe as 'evolved scope emerged during build'; do NOT characterise as Discovery failure. | Guy | Open | 17/04/2026
9 | Simplification cluster (PAYM-327–330) — rework of initial designs; SOW commits to one build cycle. | MED | CR-3 / Shared | 50/50 share as goodwill; avoid precedent of full absorption. | Account Lead | Open | 17/04/2026
10 | PPT2 timing pressure — raising CRs after PPT2 completes weakens position. | HIGH | All CRs | All CRs lodged before PPT2 gate. Calendar the deadline now. | Guy + Account Lead | Open | 17/04/2026