## 1. Executive Summary
Hireup JIRA Scope Analysis — Finalised Report
Project | Hireup Payroll Implementation
SOW Reference | SOW No. 20250717H
SOW Value | $170,000 (fixed price)
SOW Date | August 2025
Analysis Date | 16 April 2026
Prepared By | 2cloudnine
Review Method | Multi-agent independent review (3 passes)
CLASSIFICATION SUMMARY
Category | Count | % of Total
In Scope | 65 | 66%
Scope Creep / Feature Request | 19 | 19%
Borderline | 15 | 15%
Total | 99 | 100%
COMMERCIAL EXPOSURE SUMMARY
| Low Estimate | High Estimate | % of SOW
Scope Creep CRs (19 tickets) | $44,000 | $59,000 | 26-35%
Borderline — Negotiate (7 tickets) | $10,000 | $18,000 | 6-11%
Borderline — CR (3 tickets) | $5,000 | $10,000 | 3-6%
Borderline — Absorb (5 tickets) | $0 | $0 | Goodwill
Goodwill Concessions | ($13,000) | ($20,000) | Relationship investment
Net Recoverable Target | $46,000 | $67,000 | 27-39%
RECOMMENDED CR PACKAGING
CR | Description | Est. Value | Priority
CR-1 | Sleepover Engine Extension (7 tickets) | $20k-$25k | Raise immediately — strongest position
CR-2 | Portable LSL Compliance (3 tickets) | $25k-$35k | Raise immediately — zero ambiguity
CR-3 | Enhancements & Integrations bundle (9 tickets) | $14k-$20k | Raise after CR-1/CR-2 — negotiation flex
| Package discount (all 3 CRs) | 10-15% off | Incentivise single approval
KEY FINDINGS
# | Finding | Commercial Impact
1 | Sleepover Engine Extension (7 tickets) — SOW Gap 2 is narrowly worded: 'compliance hours at the lower rate'. Minimum top-ups, 18+ hour logic, back-to-back scenarios, OT aggregation, and midday penalties are all beyond this. | Largest CR — $20-25k
2 | Portable LSL (3 tickets) — New compliance stream not in SOW, Requirements Workbook, or Discovery Workbook. | Separate CR — $25-35k
3 | Hibiscus Release (PAYM-262) — SOW Section 5 Assumption 8 explicitly excludes future product releases. | CR required for any adoption work
4 | Simplification Cluster (4 tickets, PAYM-327-330) — Rework of initial designs. SOW commits to one build cycle. Shared accountability. | Negotiate 50/50 cost share
5 | Custom UI Widget (PAYM-334) — Already built per JIRA comments. Must be commercially reconciled. | Reconcile as consumed work
6 | Min Contracted Hours (PAYM-271) — JIRA comments acknowledge 'most likely will be a change request'. | CR — client pre-acknowledges
TOP ACTIONS
# | Action | Timing
1 | Raise CR-1 (Sleepover) and CR-2 (Portable LSL) with Hireup | Before PPT2 completes
2 | Resolve Simplification cluster (327-330) — shared accountability discussion | This week
3 | Flag PAYM-334 (custom widget) — already built, must be reconciled | Next commercial meeting
4 | Absorb 5 borderline items as goodwill to strengthen CR positions | Proactively communicate
5 | Prepare formal CR documentation with SOW clause citations | Before client meeting
SOW SCOPE REFERENCE
Section | Scope
3.1 | Project Management and Governance
3.2 | Discovery and Design (SCHADS MA000100 interpretation)
3.3 | Installation and Configuration (Payroll, Award Interpretation, GL/Netsuite, Salesforce UI)
3.4 | Data Migration (one UAT, one pre-Go-Live)
3.5 | Testing (functional testing, UAT, parallel runs — 2 full pay cycles)
3.6 | Training (end-user and administrator)
3.7 | Go-Live and Post Go-Live Support (hypercare — 2 full pay cycles)
3.8 | Consultant Support (meetings, ad hoc, tech support for Hireup integration)
SOW SECTION 4 — GAP DELIVERABLES
Gap | Description
1 | Day Penalties / Loading (midnight crossing fix)
2 | Sleepover Booking Configuration (compliance hours at lower rate)
3 | Broken Shift — Rest break >= 10 hour ends a broken shift
4 | Broken Shift Across Pay Periods
5 | Consolidated Payslips for Retrospective Bookings
6 | Short Shifts
7 | Discretionary Allowance display on pay advice
Flame Trees Release
Public Holiday Trigger (location-based)
Pay Batch Automation
DOCUMENT ABBREVIATIONS
Abbreviation | Document
SOW | Hireup SOW — Final — August 25.docx (SOW No. 20250717H)
RW | Requirements workbook — Hireup Requirements sheet
RW-PE | Requirements workbook — Project Evolution sheet
DW | Payroll Discovery Workbook FINAL 20260115.xlsx
RAID | Hireup — RAID.xlsx
TL | Timeline (version 3) High Level.xlsx

## 2. All Tickets
Ticket | Summary | Type | Status | Priority | Classification | Source References | Explanation
PAYM-6 | Project Planning | Epic | New | Medium | In Scope | SOW 3.1; TL 'Original Timeline' — Project Governance row | SOW 3.1 explicitly includes project management activities. Parent epic.
PAYM-8 | Testing | Epic | New | Medium | In Scope | SOW 3.5; TL 'Revised PPT' — PPT1/PPT2/PPT3 rows | SOW 3.5 commits to functional testing and parallel runs. Parent epic.
PAYM-9 | Go Live | Epic | New | Medium | In Scope | SOW 3.7; TL 'Revised PPT' — Go-Live section | SOW 3.7 covers go-live preparation and hypercare. Parent epic.
PAYM-12 | Schedule Reporting Workshop | Task | New | Medium | In Scope | SOW 3.2; SOW 3.6; RW 'Custom reports and dashboards' (Custom) | Discovery workshop and training on reports/dashboards.
PAYM-45 | Minimum Sleepover is not working as expected | Bug | Open | High | Scope Creep | SOW Gap 2 wording does not cover this | Minimum sleepover top-up (IFA-specific) is bespoke business logic beyond Gap 2 wording.
PAYM-49 | SIT Exit Sign Off | Task | New | Medium | In Scope | SOW 3.5; TL 'Original Timeline' — SIT row | Standard testing gate confirming readiness for UAT.
PAYM-53 | REGRESSION Defect Analysis & Reporting | Task | New | Medium | In Scope | SOW 3.5; TL 'Revised PPT' — Post PPT defect resolution rows | Regression analysis integral to parallel runs.
PAYM-69 | PPT Run 1 (Historical Closed Period) | Task | New | Medium | In Scope | SOW 3.5; TL 'Revised PPT' — PPT1 row | SOW 3.5 commits to parallel run support.
PAYM-70 | PPT2 Run 2 (Current Open Period) | Task | New | Medium | In Scope | SOW 3.5; TL 'Revised PPT' — PPT2 row | Second parallel run using current open period.
PAYM-71 | PPT Run 3 (Cutover Simulation) | Task | New | Medium | In Scope | SOW 3.5; TL 'Revised PPT' — PPT3 row | Final parallel run before go-live.
PAYM-72 | PPT Reconciliation and Variance Analysis | Task | New | Medium | In Scope | SOW 3.5; RW 'Parallel runs & validation'; TL reconciliation row | Core purpose of parallel runs.
PAYM-73 | PPT Defect Resolution & Re Runs | Task | New | Medium | In Scope | SOW 3.5; TL 'Revised PPT' — Post PPT defect resolution rows | Defect resolution between parallel runs.
PAYM-74 | PPT Exit Sign Off | Task | New | Medium | In Scope | SOW 3.5; TL 'Revised PPT' — Go/No-go decision rows | Formal gate confirming system ready for go-live.
PAYM-80 | Delivery of Training | Task | In Review | Medium | In Scope | SOW 3.6; TL 'Revised PPT' — PAYM-80 row | SOW 3.6 commits to in-person end-user sessions.
PAYM-87 | PIA Privacy Assessment for 2c9 | Task | Open | Medium | In Scope | SOW Appendix A — Security; RW 'Roles and permissions' | SOW Appendix A commits to security activities.
PAYM-90 | Support Model Approach and Sign Off | Task | Blocked | Medium | In Scope | SOW 3.7; TL 'Original Timeline' — Support Model row | SOW 3.7 covers post go-live support.
PAYM-91 | Support Model Content and Sign Off | Task | New | Medium | In Scope | SOW 3.7; TL 'Original Timeline' — Support Model Content row | Content deliverable for support model.
PAYM-92 | PPT Portal Access & Review | Task | In Review | Medium | In Scope | RW 'Employee portal capabilities' (Standard); DW 'EMPLOYEE & APPROVER PORTAL' | Portal is Standard in RW.
PAYM-98 | Finance GL Report Build — Location requirements | Task | Open | Medium | Scope Creep | Not in SOW, RW, or DW | Dual-location columns on GL report — custom enhancement not in discovery.
PAYM-112 | [Test] Bank ABA File | Story | In Review | Medium | In Scope | SOW 3.3; RW 'Master payroll data setup'; TL Build 2 row | Standard payroll output. Timeline lists as build item.
PAYM-113 | [Test] Super Clearing File | Story | In Review | Medium | In Scope | SOW 3.3; RW 'Stapled super' (Custom); TL Build 3 row | Standard payroll integration. Timeline lists as build item.
PAYM-114 | [Test] ATO Integration | Story | New | Medium | In Scope | SOW 3.3; TL Build 4 row | Standard payroll compliance. Timeline lists as build item.
PAYM-115 | [Test] GL Integration (Netsuite) | Story | New | Medium | In Scope | SOW 3.3 ('GL and cost code set up'); TL Build 5 row | SOW 3.3 explicitly names GL/Netsuite.
PAYM-121 | Build Integration — Project Evolution CR1 | Story | In Review | Medium | In Scope | RW-PE 'Project Evolution'; TL Build 11 ('CR1 SO'); RAID R01 | CR1 formally approved. Timeline records sign-off.
PAYM-123 | SACS Project Codes | Task | Open | Low | In Scope | RW 'Short shift and penalty pay codes' (Custom); SOW Gap 7 | RW includes Custom user story for pay codes.
PAYM-137 | Community Portal approvers & Payroll system users | Task | Open | Medium | In Scope | RW 'Employee portal capabilities'; RW 'Roles and permissions'; DW 'SYSTEM USERS' | Portal and permissions are Standard in RW.
PAYM-145 | Discuss change of State and LSL | Task | Open | Medium | In Scope | SOW 3.2; RW 'Dual leave loading'; DW 'LEAVE RULES' | Discovery activity for LSL accrual.
PAYM-151 | Friday Booking reconciliation report | Task | Open | Medium | Borderline | RW 'Custom reports and dashboards' — self-service training | Could be training outcome. If 2c9 builds, additional work.
PAYM-152 | Sleepover Timing — Hireup internal changes | Task | New | Low | In Scope | SOW Gap 2; SOW 3.1 (Project Management) | Project management — tracking dependencies.
PAYM-159 | Setup custom fields for Portable LSL Registration | Task | Open | Low | Scope Creep | Not in SOW, RW, or DW | Portable LSL not in any scope document.
PAYM-166 | [Nice to have] Slack integration for Payroll alerts | Task | New | Medium | Scope Creep | Not in SOW, RW, or DW | No scope document mentions Slack. Tagged 'Nice to have'.
PAYM-167 | Hireup custom Payslip template | Task | In Review | High | In Scope | SOW Gap 7; RW 'Consolidated pay advice' (Custom) | SOW Gap 7 requires all-inclusive rate on payslips.
PAYM-172 | Include late approvals in Pay Batch [Training] | Task | Open | Medium | In Scope | SOW 3.6; RW 'Off-cycle pays'; TL PAYM-172 row | Training on late-approved bookings. Timeline references ticket.
PAYM-173 | Complete Portable LSL Workbook | Task | Open | Medium | Scope Creep | Not in SOW, RW, or DW | Portable LSL not in any scope document.
PAYM-174 | Sleepover Timing — FairWork award changes | Task | New | Low | In Scope | SOW 3.1; SOW 3.2; RAID risks | Tracking/awareness only — no build requested.
PAYM-183 | Broken shift & Sleepover bookings incorrect | Bug | In Progress | High | In Scope | SOW Gap 2 + Gap 3; RW 'Broken shift logic'; RW 'Sleepovers' | Spans two SOW gap deliverables.
PAYM-193 | Comms to Business to approve retros/tidy data | Task | New | Medium | In Scope | SOW 3.7; RW 'Payroll cutoff and approval workflow' | Go-live preparation.
PAYM-194 | Pay batch creation / automation | Story | In Review | Medium | In Scope | SOW Flame Trees; SOW Section 5 Assumption 8; RW (3 user stories) | SOW explicitly lists as Flame Trees deliverable.
PAYM-207 | Determine best way to enter On-call Allowances | Task | Open | Medium | In Scope | SOW 3.3; DW 'ALLOWANCE PAY CODES'; TL PAYM-207 row | On-call allowances in DW. Timeline references ticket.
PAYM-214 | Test PPT Work schedules and minimum hours | Task | Blocked | Medium | In Scope | SOW 3.5; RW 'Payroll calendar and cut-off'; DW 'PAY SCHEDULES' | Functional testing within SOW 3.5.
PAYM-217 | Review licences and allocations | Task | New | Medium | In Scope | SOW 3.1; SOW 3.7; DW 'SYSTEM USERS' | Standard project governance and go-live readiness.
PAYM-219 | Finalise Public holiday calendars | Task | In Review | Medium | In Scope | SOW Flame Trees (PH Trigger); RW 'PH by shift location'; DW PH sheets | PH Trigger is Flame Trees deliverable.
PAYM-220 | Confirmation of retro approach — paper to ELT | Task | Open | Medium | In Scope | SOW 3.7; SOW 3.1 | Go-live preparation governance.
PAYM-221 | Audit log requirements | Task | In Review | Medium | In Scope | RW 'Audit history tracking' (Standard); SOW Appendix A; TL PAYM-221 row | RW Standard. SOW Appendix A security logging.
PAYM-229 | Sync Data from 2c9 to Platform | Epic | New | Medium | In Scope | RW 'Outbound pay results'; RW 'Return of pay results'; TL Build 10; SOW 3.8 | RW has Standard and Custom user stories.
PAYM-232 | Auto-approve workflow for open timesheets | Story | New | Medium | Borderline | RW 'Payroll cutoff'; RW 'Pay batch triggering' | Auto-approval is custom scheduled automation beyond standard config.
PAYM-233 | Configure PROD Instance | Epic | In Review | Medium | In Scope | SOW 3.3; TL production uplift rows | SOW 3.3 covers installation and configuration.
PAYM-234 | SCHADS Award rules build | Epic | Open | High | In Scope | SOW 3.2 (SCHADS MA000100); SOW 3.3; RW 10+ user stories; DW 'MA000100 SCHADS' | SOW 3.2 specifically names SCHADS.
PAYM-235 | Configure Payroll engine | Epic | In Review | High | In Scope | SOW 3.3; RW multiple payroll stories; DW multiple sheets | SOW 3.3 covers payroll configuration. Parent epic.
PAYM-241 | Build Portable LSL Reports (5 states) | Task | Open | Medium | Scope Creep | Not in SOW, RW, or DW | Portable LSL not in scope. 5 state reports — significant effort.
PAYM-242 | Configure protected earnings | Task | In Review | Medium | In Scope | SOW 3.3; DW 'DEDUCTION PAY CODES'; RW 'Master payroll data setup' | Standard payroll deduction configuration.
PAYM-243 | [UAT] Test Project Evolution CR Changes | Task | New | Medium | In Scope | SOW 3.5; RW-PE; TL Build 11; RAID R01 | Testing of formally approved CR1.
PAYM-255 | Post Go Live items | Epic | New | Medium | In Scope | SOW 3.7; TL Post Go-Live Activities | SOW 3.7 includes hypercare. Parent epic.
PAYM-261 | End User Training | Epic | New | Medium | In Scope | SOW 3.6; TL Training section | SOW 3.6 commits to training. Parent epic.
PAYM-262 | Quarterly Release — Hibiscus | Story | New | Medium | Scope Creep | SOW Section 5 Assumption 8 excludes future releases | 'Future product releases are not included'. Any work is a CR.
PAYM-271 | Solution for PPT Min Contracted Hours | Task | Open | Medium | Scope Creep | Not in SOW, RW, or DW | Custom solution. JIRA acknowledges 'most likely a change request'.
PAYM-272 | Solution for Sleepover bookings crossing midday | Task | New | Medium | Borderline | SOW Gap 2; RW 'Sleepovers' | Interim workaround in scope; permanent solution is scope creep.
PAYM-273 | Sleepover — incorrect payment first & active hours | Bug | Open | High | Borderline | SOW Gap 2; RW 'Sleepovers and disturbances' | Base bug in scope; midnight-crossing expansion beyond basic config.
PAYM-278 | Payee Exit, GL, STP [Training] | Task | Open | Medium | In Scope | SOW 3.6; TL PAYM-278 row | Training session. Timeline references ticket.
PAYM-279 | Process for FDVL & Pay advices | Task | Open | Medium | Scope Creep | Not in SOW, RW, or DW | FDVL not in any scope document.
PAYM-280 | Process to create new pay codes & ensure rates generated | Task | New | Medium | Scope Creep | Not in SOW, RW, or DW | Operational documentation/tooling beyond SOW handover.
PAYM-281 | Define template for data load of leave balances | Task | In Review | Medium | In Scope | SOW 3.4 ('Templates provided by 2cloudnine'); DW 'LEAVE RULES' | SOW 3.4 explicitly offers templates.
PAYM-293 | Pay trans import defaulting to $34.59 | Bug | In Progress | High | Borderline | SOW 3.3; TL Build 8 | Import bug in scope; conflates with CAG/PPL rates (out of scope).
PAYM-294 | Public holidays incorrectly tagged (UX Issue) | Bug | In Progress | Low | In Scope | SOW Flame Trees (PH Trigger); RW 'PH by shift location'; DW PH sheets | PH calendar defect. Flame Trees deliverable.
PAYM-296 | SACS Short shifts calcs incorrect | Bug | In Progress | High | In Scope | SOW Gap 6; RW 'Short shift detection and uplift' (Custom) | SOW Gap 6 lists short shifts. Failure in gap deliverable.
PAYM-299 | Reports and Dashboard, Portal [Training] | Task | Open | Medium | In Scope | SOW 3.6; RW 'Standard payroll reports'; RW 'Custom reports' | Training on reports, dashboards, portal.
PAYM-301 | Investigate Error Log for Bulk Approval | Task | New | Medium | In Scope | SOW 3.5; SOW 3.8 | Standard defect triage during testing.
PAYM-310 | Public holiday part day — Afternoon shift not recognised | Task | Open | Medium | In Scope | SOW Flame Trees (PH Trigger); RW 'PH by shift location'; DW PH sheets | Part-day PH defect. Flame Trees deliverable.
PAYM-311 | Default pay rates for CAG & PPL | Task | In Review | High | Borderline | Partially — SOW 3.3; DW does not list CAG/PPL | Config is standard but categories not in Discovery Workbook.
PAYM-312 | Sleepovers > 18 hours in duration incorrect | Bug | In Progress | High | Scope Creep | SOW Gap 2 wording does not cover this | 18+ hour sleepovers — complex engine work beyond Gap 2.
PAYM-313 | Sleepovers > 18 hours & back-to-back Sleepovers | Bug | In Progress | High | Scope Creep | SOW Gap 2 wording does not cover this | Back-to-back sleepovers — further beyond Gap 2 than PAYM-312.
PAYM-314 | Daily OT Calc incorrect | Bug | Open | High | In Scope | SOW Gap 1; RW 'Overnight shift logic' (Custom) | Exactly matches SOW Gap 1 midnight-crossing scenario.
PAYM-318 | Short Shift Saturday & PH payment incorrect | Bug | Open | High | In Scope | SOW Gap 6; RW 'Short shift detection and uplift' (Custom) | Defect in SOW Gap 6 deliverable.
PAYM-319 | Minimum Sleepover Rates incorrect | Bug | Open | High | Scope Creep | SOW Gap 2 wording does not cover this | Minimum sleepover top-up concept not in SOW or RW.
PAYM-324 | Daily OT not triggered with Day booking + Sleepover | Bug | In Progress | High | Scope Creep | SOW Gap 2 wording does not cover this | OT aggregation issue, not sleepover configuration.
PAYM-325 | Sleepover crossing midday — incorrect shift penalty | Bug | Open | Medium | Scope Creep | SOW Gap 2 wording does not cover this | System constraint workaround, not sleepover config.
PAYM-326 | Create new pay code — Min Sleepover Mon-Fri | Task | In Review | High | Scope Creep | SOW Gap 2 wording does not cover this | New pay code for mechanism not in SOW.
PAYM-327 | [Simplification 1] Consolidate Pay Code Structure | Task | In Review | High | Borderline | Partially — RW 'rationalise names'; SOW 3.3 | Architecture rework exceeds 'rationalise names'. Re-architecture.
PAYM-328 | [Simplification 2] Decouple Sleepover/Remote from Broken Shift | Task | In Review | Medium | Borderline | Partially — SOW Gaps 2, 3; RW Broken shift + Sleepovers | Rework of design. SOW commits to one build cycle.
PAYM-329 | [Simplification 3] Standardise Discretionary Allowance | Task | In Review | Medium | Borderline | Partially — SOW Gap 7 | Second iteration of Gap 7. Redesign, not refinement.
PAYM-330 | [Simplification 4] Review Broken/Split Shift Logic | Task | In Review | Medium | Borderline | Partially — SOW Gaps 3, 4, 6; RW broken/short shift stories | Rework due to design complexity.
PAYM-333 | Review Apex code / Changes to flows impacts | Task | New | Medium | Scope Creep | Not in SOW, RW, or DW | Code audit — SOW covers training/handover, not auditing.
PAYM-334 | Create UI Widget for adhoc timesheet entries | Task | New | Medium | Scope Creep | Not in SOW, RW, or DW | Custom LWC — not 'configuration'. Already built.
PAYM-335 | Investigate adjustments for Payee leave events | Task | In Review | Medium | Borderline | Partially — RW 'Dual leave loading' says 'pay the higher' | May be config defect. System defaulting to wrong rate.
PAYM-336 | Picklist of Allowance pay codes | Task | In Review | Medium | In Scope | SOW 3.3; DW 'ALLOWANCE PAY CODES' | Standard Salesforce picklist configuration.
PAYM-337 | Hireup custom Payslip Email body | Task | Open | High | Borderline | Partially — SOW Gap 7; SOW Deliverables | Email wrapper for in-scope payslip. Branding/legal beyond config.
PAYM-340 | End of year processing [Support/Training] | Task | New | Medium | In Scope | SOW 3.6; SOW 3.7 | Standard EOFY processing training.
PAYM-341 | Production User Review | Task | In Review | Medium | In Scope | SOW 3.7; SOW Appendix A — Security; DW 'SYSTEM USERS' | Go-live readiness and security obligation.
PAYM-342 | Align on Reversed Transactions display on Pay Advice | Task | In Review | Medium | Borderline | Partially — SOW Gap 5; RW 'Consolidated pay advice' | Gap 5 is consolidation, not reversal display redesign.
PAYM-344 | Public holiday under paid of SW L1 | Bug | New | High | In Scope | SOW Flame Trees (PH Trigger); SOW 3.3 | PH underpayment is a rate calculation defect.
PAYM-345 | Update missing BSBs in Prod | Bug | Open | Medium | In Scope | SOW 3.3; RW 'Master payroll data setup' | BSB data integrity for Bank ABA payments.
PAYM-347 | Update MV Allowance to $1.04 per KM | Task | In Review | High | Borderline | SOW 3.3; DW 'ALLOWANCE PAY CODES' | Discretionary 5c increase. Trivial but sets precedent.
PAYM-351 | Submitting Leave fails — EmailException error | Task | Open | Medium | In Scope | RW 'Employee portal capabilities'; SOW 3.3 | Portal is Standard. Leave failure is product defect.
PAYM-354 | Production Org API Limits | Task | Open | Medium | Scope Creep | Not in SOW, RW, or DW | Operational monitoring — not a build task.
PAYM-356 | New Training pay code — no associated pay rate | Bug | New | Medium | In Scope | SOW 3.3; RW 'Short shift and penalty pay codes' | Config defect — pay code producing $0.
PAYM-357 | Review and check GL Account codes | Task | New | Medium | In Scope | SOW 3.3 ('GL and cost code set up') | SOW 3.3 includes GL setup. Standard QA.
PAYM-358 | Separate pay code for Training (GL 50710/50720) | Task | New | High | Borderline | Partially — RW 'Remote work and training' (Custom) | RW backs dedicated codes; GL mapping is the extension.
PAYM-176 | 2c9 Prod Instance set up | Task | Done | Medium | In Scope | SOW 3.3 (Installation and Configuration) | Production org setup with 2cloudnine packages + Hireup custom flows. Core deployment activity — Guy confirmed packages installed 9 Feb; Heidi marked Done 16 Apr (core config complete). Added via verification against Jira report 20260414 PDF.
PAYM-277 | Broken Shift Allowance not triggered when first shift crosses midnight | Bug | Not a bug | High | In Scope | SOW Gap 3 (Broken Shift); 18 Feb 2026 workshop decision | Resolved 'Not a bug' 2 Apr 2026. Hireup attempted to re-litigate calendar-day broken-shift logic as rolling-12-hour. Heidi's 1 Apr comment: 'agreed by all on 18 Feb to use calendar day — highly significant change in scope. If rolling 12-hour is now needed, raise as formal CR.' Scope line held — no commercial impact. Added via verification against Jira report 20260414 PDF.

## 3. Scope Creep — CR Themes
Scope Creep — Change Request Themes
19 tickets classified as Scope Creep, grouped into 9 commercial themes with defensibility assessment
Theme | Tickets | Count | Defensibility (1-5) | Commercial Value | Est. $ Range | Why Out of Scope | Recommended CR Wording | Likely Client Pushback
Sleepover Engine Extension | PAYM-45, 312, 313, 319, 324, 325, 326 | 7 | 3-4 | L | $20k-$25k | SOW Gap 2 only covers 'compliance hours at the lower rate'. These extend into minimum top-ups, 18+ hour logic, back-to-back scenarios, OT aggregation, midday penalties, new pay codes. | Design, build, test, and deploy an enhanced sleepover interpretation solution covering minimum sleepover top-up logic, long-duration sleepovers, back-to-back sleepovers, OT aggregation, midday penalty treatment, and pay-code changes. | 'Sleepovers were in scope' — but Gap 2 wording is narrow
Portable LSL Compliance | PAYM-159, 173, 241 | 3 | 5 | L | $25k-$35k | Portable LSL not referenced in SOW, Discovery Workbook, or Requirements Workbook. New compliance workstream. | Design and implement Portable Long Service Leave support including data model changes, requirement definition, and reporting for required state schemes. | Minimal — entirely new domain
Future Product Release (Hibiscus) | PAYM-262 | 1 | 5 | L | Deferrable | SOW Section 5 Assumption 8 explicitly excludes future product releases other than Flame Trees. | Plan, test, and coordinate Hibiscus release adoption including impact assessment, configuration uplift, regression testing, and deployment support. | None — SOW Assumption 8 is explicit
Minimum Contracted Hours | PAYM-271 | 1 | 5 | M | $10k-$15k | Custom solution for work schedules and automatic top-up not in SOW or discovery artefacts. | Design and implement minimum contracted hours solution for PT/permanent workers including work schedule design, top-up calculation, leave interaction, testing, and deployment. | None — client acknowledges in JIRA as CR
FDVL / Pay Advice Compliance | PAYM-279 | 1 | 4 | S | $5k-$8k | FDVL processing and pay advice suppression not in any scope document. | Define, configure, and test FDVL process including payroll treatment, pay advice rules, security/privacy controls, and user guidance. | 'FDVL is a legal obligation, you should have known'
GL Reporting Enhancement | PAYM-98 | 1 | 3 | S | $5k-$8k | SOW covers GL and Netsuite export but not custom dual-location reporting. | Design and deliver enhanced GL export/report with both primary location and service-delivery location fields. | 'GL reporting was in scope, locations are just config'
Slack / Alerting Integration | PAYM-166 | 1 | 5 | S | $5k-$8k | No scope document mentions Slack or alerting integrations. Ticket tagged 'Nice to have'. | Design and implement Slack-based payroll alerting for agreed event triggers, message routing, and support procedures. | None — client tagged 'Nice to have'
Operational Tooling & Monitoring | PAYM-280, 333, 354 | 3 | 3-5 | M | $8k-$12k | BAU enablement items: pay-code tooling, code/flow audit, API monitoring. Outside implementation deliverables. | Post-implementation operational enablement: BAU payroll admin tooling, technical audit of custom code/flows, and production API monitoring. | 'This is just handover documentation'
Custom UI — Ad Hoc Timesheet | PAYM-334 | 1 | 4 | L | $15k-$20k | SOW allows configuration of Salesforce UI, not bespoke LWC widget development. Already built. | Design, build, test, and deploy a custom Salesforce UI component for ad hoc timesheet entry workflows. | 'We need this for go-live' — already built, reconcile
NOTES
1. PAYM-334 has already been built — reconcile as consumed work. Include in CR-3 at reduced rate (50-60%).
2. PAYM-166 is the clearest pure feature request — the ticket itself says 'Nice to have'.
3. The sleepover cluster (7 tickets) should be handled as one packaged CR, not seven separate discussions.
4. The Simplification cluster (PAYM-327-330) is Borderline but has strong 'one build cycle' argument — see Borderline tab.
5. Portable LSL (3 tickets) has the highest defensibility — not mentioned in any scope document whatsoever.
6. Total estimated scope creep value: $44k-$59k (26-35% of $170k SOW).

## 4. Borderline
Borderline Tickets — Assessment and Recommended Actions
15 tickets requiring commercial discussion — each should be resolved before client presentation
Ticket | Summary | Priority | Lean (% In Scope) | Risk Level | Commercial Approach | Source References | Explanation | Rationale
PAYM-151 | Friday Booking reconciliation report | Medium | 40% | L | CR | RW 'Custom reports and dashboards' | Could be training outcome. If 2c9 builds, additional work. | Report building is client-side post-training
PAYM-232 | Auto-approve workflow for open timesheets | Medium | 55% | M | Negotiate | RW 'Payroll cutoff'; RW 'Pay batch triggering' | Auto-approval is custom scheduled automation beyond standard config. | Need from in-scope cutoff; scheduled job is net-new
PAYM-272 | Sleepover bookings crossing midday | Medium | 65% | M | Absorb | SOW Gap 2; RW 'Sleepovers' | Interim workaround in scope; permanent fix is scope creep. | Interim workaround falls within Gap 2
PAYM-273 | Sleepover — incorrect payment first & active hours | High | 60% | M | Absorb | SOW Gap 2; RW 'Sleepovers and disturbances' | Base bug in scope; midnight-crossing expansion beyond basic config. | Base bug clearly in scope; edge is natural extension
PAYM-293 | Pay trans import defaulting to $34.59 | High | 50% | H | Negotiate | SOW 3.3; TL Build 8 | Import bug in scope. Conflates with CAG/PPL rate requirements. | Import bug is ours; root cause tangles with undiscovered rates
PAYM-311 | Default pay rates for CAG & PPL | High | 35% | L | CR | Partially — SOW 3.3; DW does not list CAG/PPL | Config is standard but categories not in Discovery Workbook. | CAG/PPL absent from DW — not agreed
PAYM-327 | [Simplification 1] Consolidate Pay Code Structure | High | 55% | H | Negotiate | RW 'rationalise names'; SOW 3.3 | Architecture rework exceeds 'rationalise names' user story. | Rework — original designs failed for both parties
PAYM-328 | [Simplification 2] Decouple Sleepover/Remote from Broken Shift | Medium | 50% | H | Negotiate | SOW Gaps 2, 3; RW Broken shift + Sleepovers | Rework of coupling Hireup requested. SOW commits to one build cycle. | Hireup requested coupling then decoupling — shared fault
PAYM-329 | [Simplification 3] Standardise Discretionary Allowance | Medium | 60% | M | Absorb | SOW Gap 7 | Second iteration of Gap 7. First introduced non-standard logic. | Gap 7 commits to discretionary allowance — refinement
PAYM-330 | [Simplification 4] Review Broken/Split Shift Logic | Medium | 45% | H | Negotiate | SOW Gaps 3, 4, 6; RW broken/short shift stories | Rework of Gaps 3/4/6 due to design complexity. | Complexity neither party foresaw — split cost fairest
PAYM-335 | Investigate adjustments for Payee leave events | Medium | 65% | M | Absorb | RW 'Dual leave loading' says 'pay the higher' | System defaulting to 17.5% instead of higher weekend rate. | RW says 'pay the higher' — config defect
PAYM-337 | Hireup custom Payslip Email body | High | 40% | L | CR | SOW Gap 7; SOW Deliverables | Email wrapper for in-scope payslip. Branding/legal beyond config. | SOW commits to content, not custom email wrapper
PAYM-342 | Reversed Transactions display on Pay Advice | Medium | 55% | M | Negotiate | SOW Gap 5; RW 'Consolidated pay advice' | Gap 5 is consolidation, not reversal display redesign. | Gap 5 covers consolidation; reversal redesign stretches it
PAYM-347 | Update MV Allowance to $1.04 per KM | High | 70% | L | Absorb | SOW 3.3; DW 'ALLOWANCE PAY CODES' | Discretionary 5c increase. Trivial effort but sets precedent. | Trivial effort; absorbing buys goodwill
PAYM-358 | Separate pay code for Training (GL 50710/50720) | High | 45% | M | Negotiate | RW 'Remote work and training' (Custom) | RW backs dedicated codes; GL mapping is the extension. | RW supports codes; GL mapping is additive
RESOLUTION BUCKETS
Bucket | Tickets | Count | Action | Rationale
Likely Absorb | PAYM-272, 273, 329, 335, 347 | 5 | Accept as in scope or goodwill | Low cost (<40 hrs combined). Fixes defects or trivial config. Buying credibility.
Negotiate Shared Cost | PAYM-232, 293, 327, 328, 330, 342, 358 | 7 | Propose 50/50 cost share | Genuine shared accountability. Simplification cluster is critical negotiation.
Push to CR | PAYM-151, 311, 337 | 3 | Add to CR-3 or standalone mini-CR | New deliverables with no SOW anchor. Low risk of pushback.

## 5. Review Findings
Finalised Review Findings and Commercial Strategy
Independent multi-agent review — 16 April 2026
METHODOLOGY
Step | Description
1. Initial Classification | 99 JIRA tickets classified against SOW (Aug 2025), Requirements Workbook, Discovery Workbook, RAID Log, and Project Timeline. (Initial pass: 97 tickets from JIRA.xml; 2 additional tickets — PAYM-176, PAYM-277 — added 17 Apr after PDF cross-check.)
2. Multi-Agent Review (Pass 1) | Three independent agents challenged classifications: (a) SOW Gap 2 wording, (b) non-gap in-scope tickets, (c) scope creep/borderline counter-check. 23 tickets reclassified.
3. Multi-Agent Review (Pass 2) | Three finalisation agents reviewed: (a) Contractual defensibility scoring (1-5), (b) Borderline lean % and risk, (c) Commercial packaging and negotiation strategy.
4. Commercial Packaging | 19 scope creep tickets grouped into 3 Change Requests. 15 borderline tickets triaged into Absorb/Negotiate/CR buckets.
DEFENSIBILITY SUMMARY
Tier | Items | Strength | Notes
Rock-solid (5/5) | PAYM-159, 166, 173, 241, 262, 271, 333 | Very Strong | Zero contractual ambiguity. Hold firm, invoice separately.
Strong (4/5) | PAYM-45, 279, 312, 313, 319, 326, 334, 354 | Strong | Expect 'sleepovers were in scope' noise. Defend with Gap 2 wording.
Moderate (3/5) | PAYM-98, 280, 324, 325 | Softer | Client can argue 'implementation detail'. Consider conceding 280, 325.
NEGOTIATION STRATEGY
# | Recommendation
1 | Frame as partnership, not penalty. 'These requirements emerged during build and were not in the signed SOW.'
2 | Lead with CR-1 (Sleepover) and CR-2 (Portable LSL) — strongest contractual positions.
3 | Offer 10-15% package discount if client approves all three CRs together.
4 | Absorb 5 borderline tickets as goodwill concession — demonstrates reasonableness.
5 | Use Simplification cluster (327-330) as 'shared accountability' discussion — propose 50/50 split.
6 | Position CR-3 as 'items we want to deliver well rather than rush under existing budget'.
7 | PAYM-334 (custom widget): include in CR-3 at reduced rate (50-60%). First item to concede if needed.
8 | PAYM-262 (Hibiscus): flag as deferrable post go-live. Easy descope option for client.
9 | TIMING: Raise CR-1 and CR-2 NOW, before PPT2 completes. Waiting weakens position.
CONCESSION STRATEGY
Type | Items | Value | Purpose
Concede (goodwill) | PAYM-98, 280, 325 | ~$5-8k absorbed | Removes weakest arguments, strengthens credibility
Concede (borderline absorb) | PAYM-272, 273, 329, 335, 347 | ~$8-12k absorbed | Low cost items — defects or trivial config
Total goodwill investment |  | ~$13-20k | Buys credibility to hold firm on $44-59k of genuine scope creep
SOURCE DOCUMENTS
Document | Reference
SOW | Hireup SOW — Final — August 25.docx (SOW No. 20250717H, $170,000)
Requirements Workbook | HireUp — Requirements workbook (User Stories).xlsx
Discovery Workbook | HireUp — Payroll Discovery Workbook FINAL 20260115.xlsx
RAID | Hireup — RAID.xlsx
Timeline | INTERNAL Hireup Program — Copy of Timeline (version 3) High Level.xlsx
JIRA Export | JIRA.xml (138 keys, 97 in-scope PAYM tickets) + JIRA (2).xml verification export (17 Apr 2026) — added PAYM-176 and PAYM-277 after cross-check against Jira report 20260414 PDF.